## Sheet1
Project Number | Milestone | Amount | Target Invoice Date | Actual Invoice Date | Payment Received Date | Status | Description | Contract Reference | Payment Terms | Invoice Number | Percentage of Total | Billing Contact | Notes
805007 | Monthly Progress Report | 24929 | 2024-08-12 | 2024-08-12 | 2024-08-12 | Billed
804404 | MS #4 - 10% Delivery | 24778 | 2024-08-13 | 2024-08-13 | 2024-08-13 | Billed
804572 | MS #2 - 20% SuperStructure | 53759 | 2024-08-14 | 2024-08-14 | 2024-08-14 | Billed
804571 | MS #3 - 20% Electrical Rough-in | 53759 | 2024-08-15 | 2024-08-15 | 2024-08-15 | Billed
805049 | MS #1 - PO Approval | 421656 | 2024-08-16 | 2024-08-16 | 2024-08-16 | Billed
804703 | MS #3 - 15% QC | 33129 | 2024-08-21 | 2024-08-21 | 2024-08-21 | Billed
804503 | MS #3 - PDR | 480041 | 2024-08-26 | 2024-08-26 | 2024-08-26 | Billed
804273 | MS #2 - Chassis | 323280 | 2024-08-26 | 2024-08-26 | 2024-08-26 | Billed
804786 | MS #3 - 15% QC | 32693 | 2024-08-26 | 2024-08-26 | 2024-08-26 | Billed
804703 | MS #4 - 60% Delivery | 132516 | 2024-08-26 | 2024-08-27 | 2024-08-27 | Billed
804572 | MS #3 - 20% Electrical Rough-in | 53759 | 2024-08-28 | 2024-08-28 | 2024-08-28 | Billed
804198 | MS #4 - 15% Shelter Mounted | 136703 | 2024-08-29 | 2024-08-28 | 2024-08-28 | Billed
804786 | MS #4 - 60% Delivery | 130772 | 2024-08-29 | 2024-08-29 | 2024-08-29 | Billed
804652 | MS #3 - 30% Electrical Rough-In | 433657 | 2024-08-30 | 2024-08-30 | 2024-08-30 | Billed
804653 | MS #2 - 25% Superstructure | 361381 | 2024-08-30 | 2024-08-30 | 2024-08-30 | Billed
804333 | MS #1 - 100% Delivery | 347985 | 2024-08-30 | 2024-08-30 | 2024-08-30 | Billed
804488 | MS #1 - 100% Delivery | 347985 | 2024-08-30 | 2024-08-30 | 2024-08-30 | Billed
804823 | MS #3 - 15% QC | 33129 | 2024-08-30 | 2024-08-30 | 2024-08-30 | Billed
804573 | MS #2 - 20% SuperStructure | 53759 | 2024-08-30 | 2024-08-30 | 2024-08-30 | Billed
804433 | MS #4 - 15% Delivery | 78626 | 2024-08-30 | 2024-09-03 | 2024-09-03 | Billed
804088 | MOD - Roof Extension | 98081 | 2024-09-03 | 2024-09-03 | 2024-09-03 | Billed
803946 | MS #3 - 25% Delivery | 101806 | 2024-09-04 | 2024-09-04 | 2024-09-04 | Billed
804823 | MS #4 - 60% Delivery | 132516 | 2024-09-06 | 2024-09-06 | 2024-09-06 | Billed
805007 | Monthly Payment | 24929 | 2024-09-09 | 2024-09-09 | 2024-09-09 | Billed
805132 | MS #1 - 30% PO | 850800 | 2024-09-10 | 2024-09-10 | 2024-09-10 | Billed
804874 | MS #1 - 50% PO | 201455 | 2024-09-12 | 2024-09-12 | 2024-09-12 | Billed
805201 | MS #1 - 30% Proposal Drawings | 799511 | 2024-09-13 | 2024-09-13 | 2024-09-13 | Billed
803991 | MS #4 - 25% Delivery | 79443 | 2024-09-13 | 2024-09-16 | 2024-09-16 | Billed
805184 | MS #1 - 70% PO | 425645 | 2024-09-13 | 2024-09-16 | 2024-09-16 | Billed
804653 | MS #3 - 30% Electrical Rough-In | 433657 | 2024-09-18 | 2024-09-20 | 2024-09-20 | Billed
804088 | MS #4 - Superstructure | 351326 | 2024-09-20 | 2024-09-20 | 2024-09-20 | Billed
805203 | MS #1 - 50% PO | 870888 | 2024-09-20 | 2024-09-20 | 2024-09-20 | Billed
804825 | MS #3 - 65% Completion 85% Build | 143559 | 2024-09-30 | 2024-09-20 | 2024-09-20 | Billed
804826 | MS #3 - 65% Completion 85% Build | 143559 | 2024-09-30 | 2024-09-20 | 2024-09-20 | Billed
804884 | MS #2 - 30% PDR | 158699 | 2025-01-10 | 2024-09-20 | 2024-09-20 | Billed
804573 | MS #3 - 20% Electrical Rough-in | 53759 | 2024-09-30 | 2024-09-26 | 2024-09-26 | Billed
805049 | Monthly Progress #2 | 81714 | 2024-10-01 | 2024-09-26 | 2024-09-26 | Billed
804824 | MS #3 - 15% QC | 33129 | 2024-10-02 | 2024-09-26 | 2024-09-26 | Billed
804388 | MS #4 - 10% Delivery | 24778 | 2024-09-30 | 2024-09-30 | 2024-09-30 | Billed
805197 | MS #1 - 40% PO | 382857 | 2024-10-01 | 2024-10-01 | 2024-10-01 | Billed
804018 | MS #1 - 33% PO | 868429 | 2024-10-01 | 2024-10-01 | 2024-10-01 | Billed
804273 | MS #3 - Gantt Chart | 367943 | 2024-10-01 | 2024-10-01 | 2024-10-01 | Billed
804824 | MS #4 - 60% Delivery | 132516 | 2024-10-02 | 2024-10-02 | 2024-10-02 | Billed
804754 | MS #1 - Termination of Order | 48551 | 2024-10-02 | 2024-10-02 | 2024-10-02 | Billed
805197 | MS #2 - 5% Kickoff Meeting | 47857 | 2024-10-04 | 2024-10-04 | 2024-10-04 | Billed
804881 | MS #1 - 30% PO | 326044 | 2024-10-07 | 2024-10-07 | 2024-10-07 | Billed
803932 | MS #1 - 60% PO | 577448 | 2024-10-08 | 2024-10-08 | 2024-10-08 | Billed
805304 | MS #1 - 70% PO | 392407 | 2024-10-08 | 2024-10-08 | 2024-10-08 | Billed
805319 | MS #1 - 70% PO | 426973 | 2024-10-08 | 2024-10-08 | 2024-10-08 | Billed
804507 | MS #2 - 35% Superstructure | 436118 | 2024-10-07 | 2024-10-11 | 2024-10-11 | Billed
805120 | MS #1 - 30% Customer Kickoff | 189933 | 2024-10-08 | 2024-10-11 | 2024-10-11 | Billed
805132 | Monthly Progress #2 | 198520 | 2024-10-10 | 2024-10-14 | 2024-10-14 | Billed
805201 | Monthly Progress #2 | 169593 | 2024-10-14 | 2024-10-14 | 2024-10-14 | Billed
805007 | Monthly Payment | 24929 | 2024-10-09 | 2024-10-15 | 2024-10-15 | Billed
805132 | MS #1 - 30% MOD | 298879 | 2024-10-15 | 2024-10-15 | 2024-10-15 | Billed
804613 | MS #1 - 50% PO | 309429 | 2024-10-15 | 2024-10-15 | 2024-10-15 | Billed
804565 | MS #4 - 10% Delivery | 26879 | 2024-11-11 | 2024-10-18 | 2024-10-18 | Billed
804510 | MS #1 - Superstructure | 250000 | 2024-10-21 | 2024-10-22 | 2024-10-22 | Billed
804106 | MS #4 - 20% Delivery | 289105 | 2024-10-22 | 2024-10-22 | 2024-10-22 | Billed
804570 | MS #4 - 10% Delivery | 26879 | 2024-10-22 | 2024-10-22 | 2024-10-22 | Billed
804825 | MS #4 - 10% Delivery | 22086 | 2024-10-23 | 2024-10-23 | 2024-10-23 | Billed
804826 | MS #4 - 10% Delivery | 22086 | 2024-10-23 | 2024-10-23 | 2024-10-23 | Billed
804486 | MS #2 - 50% Delivery | 400359 | 2024-10-25 | 2024-10-25 | 2024-10-25 | Billed
805049 | Monthly Progress #3 | 81714 | 2024-11-01 | 2024-10-29 | 2024-10-29 | Billed
805197 | MS #3 - 10% PDR | 95714 | 2024-11-05 | 2024-11-05 | 2024-11-05 | Billed.
805040 | MS #2 - 30% PDR | 132010 | 2024-11-07 | 2024-11-07 | 2024-11-07 | Billed.
805277 | Monthly Progress #1 | 88251 | 2024-11-08 | 2024-11-07 | 2024-11-07 | Billed.
805277 | Monthly Progress #2 | 88251 | 2024-11-08 | 2024-11-07 | 2024-11-07 | Billed.
804654 | MS #2 - 25% Superstructure | 361381 | 2024-11-20 | 2024-11-11 | 2024-11-11 | Billed
805132 | Monthly Progress #3 | 268258 | 2024-11-11 | 2024-11-12 | 2024-11-12 | Billed.
805201 | Monthly Progress #3 | 169593 | 2024-11-13 | 2024-11-13 | 2024-11-13 | Billed.
805007 | Monthly Payment | 24929 | 2024-11-11 | 2024-11-15 | 2024-11-15 | Billed.
804571 | MS #4 - 10% Delivery | 26879 | 2024-11-15 | 2024-11-15 | 2024-11-15 | Billed.
803863 | MS #3 - 30% Electrical Rough-In | 187511 | 2024-11-15 | 2024-11-15 | 2024-11-15 | Billed.
805067 | MS #1 - 30% PO | 442924 | 2024-11-18 | 2024-11-18 | 2024-11-18 | Billed
804545 | MS #2 - 20% CDR | 150468 | 2024-11-19 | 2024-11-19 | 2024-11-19 | Billed
805206 | MS #2 - 20% CDR | 150468 | 2024-11-19 | 2024-11-19 | 2024-11-19 | Billed
805207 | MS #2 - 20% CDR | 150468 | 2024-11-19 | 2024-11-19 | 2024-11-19 | Billed
805387 | MS #1 - 100% PO | 62000 | 2024-11-20 | 2024-11-20 | 2024-11-20 | Billed.
804905 | MS #1 - 100% Delivery | 149915 | 2024-11-22 | 2024-11-25 | 2024-11-25 | Billed.
804452 | MS #3 - 25% Superstructure | 197850 | 2024-12-08 | 2024-11-25 | 2024-11-25 | Billed.
803533 | MS #1 - 100% Delivery | 1280998 | 2024-11-27 | 2024-11-26 | 2024-11-26 | Billed.
804088 | MS #5 - Electrical Rough In | 351326 | 2024-11-27 | 2024-11-27 | 2024-11-27 | Billed.
805197 | MS #4 - 10% CDR | 95714 | 2024-12-03 | 2024-11-27 | 2024-11-27 | Billed.
804347 | MS #1 - Contractor Plan | 661526 | 2024-11-22 | 2024-11-29 | 2024-11-29 | Billed.
805339 | MS #1 - Contractor Plan | 330763 | 2024-11-22 | 2024-11-29 | 2024-11-29 | Billed.
804347 | MS #1 - MLOU Specifications | 992289 | 2024-11-29 | 2024-11-29 | 2024-11-29 | Billed.
805339 | MS #1 - MLOU Specifications | 496145 | 2024-11-29 | 2024-11-29 | 2024-11-29 | Billed.
805049 | Monthly Progress #4 | 81714 | 2024-12-01 | 2024-12-02 | 2024-12-02 | Billed.
805132 | Monthly Progress #4 | 268258 | 2024-12-11 | 2024-12-02 | 2024-12-02 | Billed.
803750 | MS #3 - 34% Delivery | 385133 | 2024-12-03 | 2024-12-03 | 2024-12-03 | Billed.
804215 | MS #2 - Delivery | 452567 | 2024-12-16 | 2024-12-03 | 2024-12-03 | Billed.
805007 | Monthly Payment | 24929 | 2024-12-09 | 2024-12-10 | 2024-12-10 | Billed.
804664 | MS #1 - 100% Delivery | 149915 | 2024-12-11 | 2024-12-11 | 2024-12-11 | Billed.
804903 | MS #1 - 100% Delivery | 149915 | 2024-12-13 | 2024-12-13 | 2024-12-13 | Billed.
805201 | Monthly Progress #4 | 169593 | 2024-12-13 | 2024-12-13 | 2024-12-13 | Billed.
804904 | MS #1 - 100% Delivery | 149915 | 2024-12-05 | 2024-12-18 | 2024-12-18 | Billed.
806504 | Monthly Progress #1 | 30728 | 2024-12-18 | 2024-12-18 | 2024-12-18 | Billed.
804510 | MS #2 - Electrical Rough-In | 250000 | 2024-12-23 | 2024-12-18 | 2024-12-18 | Billed.
804433 | MS #5 - 5% Power Supply | 26209 | 2025-02-14 | 2024-12-18 | 2024-12-18 | Billed.
804186 | Electrical Rough-In | 242643 | 2024-12-19 | 2024-12-19 | 2024-12-19 | Billed.
804906 | MS #1 - 100% Delivery | 149915 | 2024-12-20 | 2024-12-20 | 2024-12-20 | Billed.
805304 | MS #2 - 10% PDR | 56058 | 2025-02-28 | 2024-12-20 | 2024-12-20 | Billed.
805319 | MS #2 - 10% PDR | 60996 | 2025-02-28 | 2024-12-20 | 2024-12-20 | Billed.
805184 | MS #2 - 10% PDR | 60806 | 2025-02-28 | 2024-12-20 | 2024-12-20 | Billed.
804545 | MS #3 - 20% Superstructure | 150468 | 2024-12-30 | 2024-12-26 | 2024-12-26 | Billed.
804655 | MS #2 - 25% Superstructure | 361381 | 2024-12-18 | 2024-12-30 | 2024-12-30 | Billed.
804817 | MODs | 800210 | 2024-12-30 | 2024-12-30 | 2024-12-30 | Billed.
804708 | MODs | 1087420 | 2024-12-30 | 2024-12-30 | 2024-12-30 | Billed.
804545 | MS #1 - 25% PO | 1123745 | 2024-12-31 | 2024-12-31 | 2024-12-31 | Billed.
805049 | Monthly Progress #5 | 81714 | 2025-01-01 | 2024-12-31 | 2024-12-31 | Billed.
805132 | Monthly Progress #5 | 268258 | 2025-01-10 | 2024-12-31 | 2024-12-31 | Billed.
804656 | MS #2 - 25% Superstructure | 361381 | 2025-01-12 | 2025-01-03 | 2025-01-03 | Billed.
804654 | MS #3 - 30% Electrical Rough-In | 433657 | 2025-01-31 | 2025-01-10 | 2025-01-10 | Billed.
805201 | Monthly Progress #5 | 169593 | 2025-01-13 | 2025-01-13 | 2025-01-13 | Billed.
805007 | Monthly Payment | 24929 | 2025-01-13 | 2025-01-16 | 2025-01-16 | Billed.
805197 | MS #5 - Monthly Progress | 33500 | 2025-01-16 | 2025-01-16 | 2025-01-16 | Billed.
804082 | MS #5 - 15% Delivery | 103339 | 2025-01-17 | 2025-01-16 | 2025-01-16 | Billed.
800582 | MS #2 - 20% AV and Comm Materials | 52354 | 2025-01-15 | 2025-01-17 | 2025-01-17 | Billed.
804538 | Delivery | 120786 | 2025-01-17 | 2025-01-20 | 2025-01-20 | Billed.
804539 | Delivery | 120786 | 2025-01-17 | 2025-01-20 | 2025-01-20 | Billed.
804485 | MS #3 - 34% Delivery | 385133 | 2025-01-21 | 2025-01-22 | 2025-01-22 | Billed.
804862 | MS #2 - 20% Superstructure | 58059 | 2025-01-21 | 2025-01-22 | 2025-01-22 | Billed.
805040 | MS #3 - 30% CDR | 132010 | 2025-01-20 | 2025-01-24 | 2025-01-24 | Billed.
804198 | MS #5 - 10% Delivery | 97322 | 2025-01-20 | 2025-01-24 | 2025-01-24 | Billed.
804469 | MS #1 - 100% Delivery | 481726 | 2025-01-21 | 2025-01-24 | 2025-01-24 | Billed.
804916 | MS #2 - 25% CDR | 93726 | 2025-01-21 | 2025-01-24 | 2025-01-24 | Billed.
805304 | MS #3 - 10% CDR | 56058 | 2025-03-28 | 2025-01-24 | 2025-01-24 | Billed.
804018 | MS #2 - 120 ARO | 868429 | 2025-01-29 | 2025-01-30 | 2025-01-30 | Billed.
804542 | Electrical Rough-In | 242643 | 2025-01-30 | 2025-01-30 | 2025-01-30 | Billed.
804541 | Electrical Rough-In | 242643 | 2025-01-30 | 2025-01-30 | 2025-01-30 | Billed.
805157 | MS #1 - 30% Upon Schedule Acceptance | 678413 | 2025-01-28 | 2025-01-31 | 2025-01-31 | Billed.
805049 | Monthly Progress #6 | 81714 | 2025-02-03 | 2025-02-03 | 2025-02-03 | Billed.
805132 | Monthly Progress #6 | 268258 | 2025-02-11 | 2025-02-03 | 2025-02-03 | Billed.
804572 | MS #4 - 10% Delivery | 26879 | 2025-02-04 | 2025-02-04 | 2025-02-04 | Billed.
805359 | MS #1 - 30% PO | 262459 | 2025-02-05 | 2025-02-05 | 2025-02-05 | Billed.
805184 | MS #3 - 10% CDR | 60806 | 2025-03-21 | 2025-02-11 | 2025-02-11 | Billed.
805319 | MS #3 - 10% CDR | 60996 | 2025-03-28 | 2025-02-11 | 2025-02-11 | Billed.
805201 | Monthly Progress #6 | 169593 | 2025-02-13 | 2025-02-13 | 2025-02-13 | Billed.
804655 | MS #3 - 30% Electrical Rough-In | 433657 | 2025-02-14 | 2025-02-13 | 2025-02-13 | Billed.
805197 | MS #6 - Monthly Progress #2 | 33500 | 2025-02-17 | 2025-02-17 | 2025-02-17 | Billed.
804884 | MS #3 - 30% Electrical Rough-In | 158699 | 2025-02-21 | 2025-02-19 | 2025-02-19 | Billed.
805277 | Monthly Progress #4 | 137964 | 2025-02-28 | 2025-02-20 | 2025-02-20 | Billed.
804452 | MS #4 - 25% Delivery | 197850 | 2025-02-24 | 2025-02-24 | 2025-02-24 | Billed.
804088 | MS #6 - PDI (FAT) | 351326 | 2025-02-19 | 2025-02-27 | 2025-02-27 | Billed.
805296 | MS #2 - Sales Proposal Drawings | 220940 | 2025-02-14 | 2025-02-28 | 2025-02-28 | Billed.
804273 | MS #4 - CDR | 331501 | 2025-02-28 | 2025-02-28 | 2025-02-28 | Billed.
805049 | Monthly Progress #7 | 81714 | 2025-03-01 | 2025-02-28 | 2025-02-28 | Billed.
805132 | Monthly Progress #7 | 268258 | 2025-03-10 | 2025-02-28 | 2025-02-28 | Billed.
803932 | MS #2 - 20% CDR | 77283 | 2025-03-21 | 2025-02-28 | 2025-02-28 | Billed.
805206 | MS #3 - 20% Superstructure | 150468 | 2025-03-24 | 2025-02-28 | 2025-02-28 | Billed.
803932 | MS #3 - 10% Completion | 38641 | 2025-07-21 | 2025-02-28 | 2025-02-28 | Billed.
804545 | MOD | 29250 | 2025-03-05 | 2025-03-05 | 2025-03-05 | Billed.
805331 | MS #1 - 30% PO | 259784 | 2025-03-10 | 2025-03-10 | 2025-03-10 | Billed.
804928 | MOD | 6051 | 2025-03-10 | 2025-03-10 | 2025-03-10 | Billed.
805201 | Monthly Progress #7 | 169593 | 2025-03-13 | 2025-03-13 | 2025-03-13 | Billed.
805347 | MS #2 - Kick Off Meeting | 187291 | 2025-03-14 | 2025-03-18 | 2025-03-18 | Billed.
805197 | MS #7 - Monthly Progress #3 | 33500 | 2025-03-17 | 2025-03-21 | 2025-03-21 | Billed.
804450 | MS #2 - 30% CDR | 107025 | 2025-03-21 | 2025-03-21 | 2025-03-21 | Billed.
805296 | MS#1 - 50% PO | 560000 | 2024-10-30 | 2025-03-24 | 2025-03-24 | Billed
804186 | Delivery / Acceptance | 120786 | 2025-03-17 | 2025-03-25 | 2025-03-25 | Billed.
804543 | Delivery / Acceptance | 120786 | 2025-03-17 | 2025-03-25 | 2025-03-25 | Billed.
804887 | MS #2 - 25% Electrical Rough-In | 48977 | 2025-03-21 | 2025-03-25 | 2025-03-25 | Billed.
804450 | MS #3 - 30% BOM Drop | 107025 | 2025-04-04 | 2025-03-25 | 2025-03-25 | Billed.
804510 | MS #3 - Delivery | 250000 | 2025-03-25 | 2025-03-26 | 2025-03-26 | Billed.
804881 | MS #2 - 30% PDR | 326044 | 2025-03-27 | 2025-03-27 | 2025-03-27 | Billed.
805347 | MS #3 - Superstructure | 187291 | 2025-03-28 | 2025-03-28 | 2025-03-28 | Billed.
805007 | Monthly Payment | 24929 | 2025-03-26 | 2025-03-31 | 2025-03-31 | Billed.
805067 | MS #4 - 10% Chassis Order | 147641 | 2025-03-25 | 2025-04-01 | 2025-04-01 | Billed.
805049 | Monthly Progress #8 | 81714 | 2025-04-01 | 2025-04-01 | 2025-04-01 | Billed.
805132 | Monthly Progress #8 | 268258 | 2025-04-10 | 2025-04-01 | 2025-04-01 | Billed.
805328 | MS #1 - 30% PO | 271168 | 2025-04-04 | 2025-04-04 | 2025-04-04 | Billed.
804924 | MS #1 - 100% Upon PO | 1437545 | 2025-04-04 | 2025-04-04 | 2025-04-04 | Billed.
803863 | MS #4 - 15% Completion | 93756 | 2025-04-14 | 2025-04-16 | 2025-04-16 | Billed.
805197 | MS #8 - Monthly Progress #4 | 33500 | 2025-04-16 | 2025-04-16 | 2025-04-16 | Billed.
804573 | MS #4 - 10% Delivery | 26879 | 2025-04-18 | 2025-04-16 | 2025-04-16 | Billed.
805201 | Monthly Progress #8 | 169593 | 2025-04-14 | 2025-04-17 | 2025-04-17 | Billed.
803863 | MS #5 - 25% Delivery | 156259 | 2025-04-14 | 2025-04-18 | 2025-04-18 | Billed.
805120 | MS #2 - 30% PDR | 198229 | 2025-04-18 | 2025-04-18 | 2025-04-18 | Billed.
804886 | MS #2 - 25% SuperStructure | 247224 | 2025-05-30 | 2025-04-18 | 2025-04-18 | Billed.
805214 | MS #2 - 20% Superstructure | 58059 | 2025-04-21 | 2025-04-23 | 2025-04-23 | Billed.
804708 | MS #1 - 100% Delivery | 35299 | 2025-04-21 | 2025-04-24 | 2025-04-24 | Billed.
804810 | MS #1 - 100% Delivery | 44285 | 2025-04-21 | 2025-04-24 | 2025-04-24 | Billed.
804811 | MS #1 - 100% Delivery | 55519 | 2025-04-21 | 2025-04-24 | 2025-04-24 | Billed.
804812 | MS #1 - 100% Delivery | 60013 | 2025-04-21 | 2025-04-24 | 2025-04-24 | Billed.
804708 | MOD - Doors | 3402 | 2025-04-21 | 2025-04-24 | 2025-04-24 | Billed.
804862 | MS #3 - 20% Electrical Rough-in | 58059 | 2025-05-02 | 2025-04-28 | 2025-04-28 | Billed.
805214 | MS #3 - 20% Electrical Rough-in | 58059 | 2025-05-09 | 2025-04-28 | 2025-04-28 | Billed.
803944 | MS #8 - Kick Off Meeting | 207850 | 2025-04-30 | 2025-04-30 | 2025-04-30 | Billed.
804887 | MS #3 - 25% Delivery | 48977 | 2025-04-30 | 2025-04-30 | 2025-04-30 | Billed.
805359 | MS #2 - 30% PDR | 262459 | 2025-04-30 | 2025-05-01 | 2025-05-01 | Billed.
805626 | Material | 553532 | 2025-05-01 | 2025-05-01 | 2025-05-01 | Billed.
805049 | Monthly Progress #9 | 81714 | 2025-05-01 | 2025-05-01 | 2025-05-01 | Billed.
805132 | Monthly Progress #9 | 268258 | 2025-05-12 | 2025-05-01 | 2025-05-01 | Billed.
804652 | MS #4 - 20% Delivery | 289105 | 2025-04-28 | 2025-05-02 | 2025-05-02 | Billed.
804273 | MOD - CDR | 86923 | 2025-05-30 | 2025-05-05 | 2025-05-05 | Billed.
803950-02 | MS #1 - 100% Completion | 6400 | 2025-07-31 | 2025-05-05 | 2025-05-05 | Billed.
805296 | MS #3 - PDR | 220940 | 2025-04-30 | 2025-05-06 | 2025-05-06 | Billed.
805079 | MS #1 - 30% PO | 413479 | 2025-05-09 | 2025-05-09 | 2025-05-09 | Billed.
805472 | MS #2 - 30% PDR | 69600 | 2025-05-08 | 2025-05-12 | 2025-05-12 | Billed.
805201 | Monthly Progress #9 | 169593 | 2025-05-13 | 2025-05-13 | 2025-05-13 | Billed.
804813 | MS #1 - 100% Delivery | 131908 | 2025-05-13 | 2025-05-14 | 2025-05-14 | Billed.
804884 | MS #4 - 10% Delivery | 52900 | 2025-05-13 | 2025-05-16 | 2025-05-16 | Billed.
805067 | MS #2 - 10% PDR | 147641 | 2025-05-14 | 2025-05-16 | 2025-05-16 | Billed.
805197 | MS #9 - Monthly Progress #5 | 33500 | 2025-05-16 | 2025-05-16 | 2025-05-16 | Billed.
804815 | MS #1 - 100% Delivery | 188077 | 2025-05-20 | 2025-05-20 | 2025-05-20 | Billed.
805120 | MS #3 - 30% CDR | 198229 | 2025-05-20 | 2025-05-21 | 2025-05-21 | Billed.
804507 | MS #3 - 25% Delivery | 372857 | 2025-05-19 | 2025-05-22 | 2025-05-22 | Billed.
804656 | MS #3 - Electrical Rough-In | 433657 | 2025-05-23 | 2025-05-23 | 2025-05-23 | Billed.
805615 | MS #1 - 30% Upon PO | 2695860 | 2025-05-23 | 2025-05-23 | 2025-05-23 | Billed.
805615 | MS #2 - 55% Upon PO | 4942410 | 2025-05-23 | 2025-05-23 | 2025-05-23 | Billed.
805517 | MS #1 - 30% Chassis Order | 67410 | 2025-07-08 | 2025-05-23 | 2025-05-23 | Billed.
804653 | MS #4 - 20% Delivery | 289105 | 2025-05-27 | 2025-05-29 | 2025-05-29 | Billed.
803944 | MS #10 - Integrated Master Schedule | 207850 | 2025-05-30 | 2025-05-30 | 2025-05-30 | Billed.
804816 | MS #1 - 100% Delivery | 152129 | 2025-05-30 | 2025-05-30 | 2025-05-30 | Billed.
804814 | MS #1 - 100% Delivery | 145389 | 2025-05-30 | 2025-05-30 | 2025-05-30 | Billed.
805207 | MS #3 - 20% Superstructure | 150468 | 2025-05-30 | 2025-05-30 | 2025-05-30 | Billed.
805049 | Monthly Progress #10 | 81714 | 2025-06-01 | 2025-06-04 | 2025-06-04 | Billed.
805132 | Monthly Progress #10 | 268258 | 2025-06-11 | 2025-06-04 | 2025-06-04 | Billed.
804484 | MS #3 - 34% Delivery | 385133 | 2025-06-03 | 2025-06-06 | 2025-06-06 | Billed.
804881 | MS #3 - 30% CDR | 326044 | 2025-06-09 | 2025-06-09 | 2025-06-09 | Billed.
804666 | MS #1 - 100% Delivery | 698425 | 2025-06-02 | 2025-06-13 | 2025-06-13 | Billed.
804916 | MS #3 - 25% Delivery | 93726 | 2025-06-10 | 2025-06-13 | 2025-06-13 | Billed.
805201 | Monthly Progress #10 | 169593 | 2025-06-13 | 2025-06-13 | 2025-06-13 | Billed.
805197 | MS #6 - Monthly Progress | 33500 | 2025-06-16 | 2025-06-16 | 2025-06-16 | Billed.
805203 | MS #2 - 20% Superstructure | 58059 | 2025-06-27 | 2025-06-18 | 2025-06-18 | Billed.
805067 | Monthly Progress #5 - Chassis Arrival | 147641 | 2025-08-30 | 2025-06-20 | 2025-06-20 | Billed.
800582 | MS #3 - 20% AV and Comm Delivery | 52354 | 2025-06-25 | 2025-06-23 | 2025-06-23 | Billed.
800582 | MS #4 - 10% Delivery | 26177 | 2025-06-25 | 2025-06-23 | 2025-06-23 | Billed.
805067 | MS #3 - 10% CDR | 147641 | 2025-07-30 | 2025-06-25 | 2025-06-25 | Billed.
803944 | MS #9 - Traceability Matrix | 207850 | 2025-06-25 | 2025-06-26 | 2025-06-26 | Billed.
804874 | MS #2 - 25% Superstructure | 100727 | 2025-06-26 | 2025-06-26 | 2025-06-26 | Billed.
804018 | MS #3 - 34% Delivery | 894746 | 2025-06-30 | 2025-07-01 | 2025-07-01 | Billed.
804287 | MS #4 - 10% Delivery | 420683 | 2025-06-30 | 2025-07-01 | 2025-07-01 | Billed.
804621 | MS #2 - 70% Delivery | 540643 | 2025-06-30 | 2025-07-01 | 2025-07-01 | Billed.
804731 | MS #1 - 100% Delivery | 1251680 | 2025-06-29 | TBD | TBD | [7 empty] | Customer MODs. Looking to invoice before delivery. Also, dimmable lights and thermal camera didn't make it in SPN.
806504 | EU-2 Assembly Complete | 72414 | 2025-07-07 | TBD | TBD | [7 empty] | Stop work order received 6.23.25, Response due 7/1/25.
806504 | EU-2 Test Complete | 18104 | 2025-07-07 | TBD | TBD | [7 empty] | Stop work order received 6.23.25, Response due 7/1/25.
805203 | MS #3 - 20% Electrical Rough-in | 58059 | 2025-07-07 | TBD | TBD | [7 empty] | Likely 2 week shift. Iridell pushing this back.
804347 | MS #3 - 30% Exposed Components Inspection | 248072 | 2025-07-10 | TBD | TBD | [7 empty] | Axles, tires, breaks, and slide hardware (step rails etc) are installed - looking into slide steps
804862 | MS #4 - 10% Delivery | 29030 | 2025-07-11 | TBD | TBD | [7 empty] | Waiting on ducting. Need updated PoP w/new schedule Monday
804907 | MS #1 - 100% Delivery | 507470 | 2025-07-11 | TBD | TBD | [7 empty] | Should be billed on final acceptance. Few hundred pounds overweight on rear axel
805304 | MS #4 - 10% Delivery | 56058 | 2025-07-11 | TBD | TBD | [7 empty] | Need to get more info from Josh Williams.
805347 | MS #4 - Battery Systems | 187291 | 2025-07-14 | TBD | TBD | [7 empty] | Materials issue, Shifted to October. Total at risk $2.1 M
805201 | Monthly Progress #11 | 169593 | 2025-07-14 | TBD | TBD | [7 empty] | Might change to on delivery - connect with Daniel.
805157 | MS #2 - 30% CDR | 678413 | 2025-07-15 | TBD | TBD | [7 empty] | Engineering to let us know if this is going to be feasible
805314 | MS #2 - 25% PDR | 147662 | 2025-07-15 | TBD | TBD | [7 empty] | This will not be occuring in July. ME start 10/27/2025, ME end 12/26/2026.
805359 | MS #3 - 30% CDR | 262459 | 2025-07-16 | TBD | TBD | [7 empty] | Waiting on Change Order from customer.
805528 | Chassis Delivery | 180080 | 2025-07-16 | TBD | TBD | [7 empty] | Quotes available, Requirements not dropped with transition. ME reviewing chassis.
805529 | Chassis Delivery | 92478 | 2025-07-16 | TBD | TBD | [7 empty] | Quotes available, Requirements not dropped with transition. Form 502 approved by ME
804542 | Delivery / Acceptance | 120786 | 2025-07-18 | TBD | TBD | [7 empty] | GaN/Govt site acceptance test (SAT) scheduled 7/11 - 7/17. Shift to August
805214 | MS #4 - 10% Delivery | 29030 | 2025-07-18 | TBD | TBD | [7 empty] | Lead time on ducting design change
804273 | MS #5 - Electrical Rough-In | 89716 | 2025-07-25 | TBD | TBD | [7 empty] | Customer EMI on-site test 6/24. Cant perform more until then. August
804273 | MS #6 - Mast Install | 50625 | 2025-07-31 | TBD | TBD
806503 | EU-1 Assembly Complete | 72414 | 2025-08-05 | TBD | TBD | [7 empty] | Stop work order received 6.23.25, Response due 7/1/25.
805201 | Monthly Progress #12 | 169593 | 2025-08-13 | TBD | TBD | [7 empty] | Might change to on delivery - connect with Daniel.
806503 | EU-1 Test Complete | 18104 | 2025-09-05 | TBD | TBD | [7 empty] | Stop work order received 6.23.25, Response due 7/1/25.
806503 | EU-1 Delivery | 18104 | 2025-09-05 | TBD | TBD | [7 empty] | Stop work order received 6.23.25, Response due 7/1/25.
805347 | MS #5 - Roof Complete | 187291 | 2025-09-15 | TBD | TBD | [7 empty] | Materials issue,Shifted to December. Total at risk $2.1 M
805347 | Phase 2 Final Assembly Complete | 187291 | 2025-10-14 | TBD | TBD | [7 empty] | At risk due to materials issue. Total at risk $2.1 M
805347 | Phase 3 Contractor Final Sign Off | 468227 | 2025-10-22 | TBD | TBD | [7 empty] | At risk due to materials issue. Total at risk $2.1 M
805347 | Phase 3 Factory Acceptance Test Complete | 468227 | 2025-10-29 | TBD | TBD | [7 empty] | At risk due to materials issue. Total at risk $2.1 M
805347 | Phase 3 Ship element 1 Pototype Hardware | 468227 | 2025-11-12 | TBD | TBD | [7 empty] | At risk due to materials issue. Total at risk $2.1 M
805347 | Phase 4 Range Integration and Training Support | 176629 | 2025-11-21 | TBD | TBD | [7 empty] | At risk due to materials issue. Total at risk $2.1 M
806504 | EU-2 Delivery | 18104 | 2025-11-28 | TBD | TBD | [7 empty] | Stop work order received 6.23.25, Response due 7/1/25.
805049 | Monthly Progress #11 | 81714 | 2025-07-01 | TBD | TBD
805040 | MS #4 - 10% Delivery | 52503 | 2025-07-10 | TBD | TBD | [7 empty] | Client final inspecition scheduled for 6/30
804928 | MS #1 - 100% Delivery | 872263 | 2025-07-11 | TBD | TBD | [7 empty] | Shipping 7/7. Needs to finish getting wrapped and QC
805132 | 10% Remaining Vehicle Cost | 119979 | 2025-07-11 | TBD | TBD | [7 empty] | New monthly schedule
804503 | MS #4 - Delivery | 490041 | 2025-07-14 | TBD | TBD | [7 empty] | Coming back Monday from a show. NTC and QC after that
804654 | MS #4 - 20% Delivery | 289105 | 2025-07-14 | TBD | TBD | [7 empty] | Have all NTC Hardwre. Should be good
805197 | MS #7 - Monthly Progress | 33500 | 2025-07-16 | TBD | TBD
804817 | MOD - Doors | 3402 | 2025-07-17 | TBD | TBD | [7 empty] | Working on Sprinters first.
804817 | MS #1 - 100% Delivery | 263625 | 2025-07-17 | TBD | TBD | [7 empty] | Working on Sprinters first.
804818 | MS #1 - 100% Delivery | 347368 | 2025-07-17 | TBD | TBD | [7 empty] | Working on Sprinters first.
804819 | MS #1 - 100% Delivery | 365977 | 2025-07-17 | TBD | TBD | [7 empty] | Working on Sprinters first.
804820 | MS #1 - 100% Delivery | 370630 | 2025-07-17 | TBD | TBD | [7 empty] | Working on Sprinters first.
804821 | MS #1 - 100% Delivery | 384587 | 2025-07-17 | TBD | TBD | [7 empty] | Working on Sprinters first.
804822 | MS #1 - 100% Delivery | 389239 | 2025-07-17 | TBD | TBD | [7 empty] | Working on Sprinters first.
804655 | MS #4 - 20% Delivery | 289105 | 2025-07-21 | TBD | TBD
804545 | MS #4 - 10% Delivery | 75234 | 2025-07-30 | TBD | TBD | [7 empty] | Waiting for NTC hardware kits. customer coming for acceptance 7/22-7/24.
805206 | MS #4 - 10% Delivery | 75234 | 2025-07-30 | TBD | TBD | [7 empty] | Waiting for NTC hardware kits, other parts. customer coming for acceptance 7/22-7/24.
805331 | MS #2 - 30% CDR | 259784 | 2025-07-31 | TBD | TBD | [7 empty] | Moved up based on customer request
805049 | Monthly Progress #12 | 81714 | 2025-08-01 | TBD | TBD
805306 | MS #2 - 20% SuperStructure | 58059 | 2025-08-11 | TBD | TBD
805132 | 10% Remaining Vehicle Cost | 119979 | 2025-08-11 | TBD | TBD
804264 | MS #2 - 20% CAD Completion | 115200 | 2025-08-15 | TBD | TBD | [7 empty] | Mid-August. Fab start in September. Assembly 9/15. Look into why this was the milestone
805197 | MS #10 - Monthly Progress #6 | 33500 | 2025-08-18 | TBD | TBD
804450 | MS #4 - 10% Acceptance at Factory | 35675 | 2025-08-21 | TBD | TBD
804450 | MS #5 - 5% Delivery of Final Docs | 17838 | 2025-08-21 | TBD | TBD | [7 empty] | Meeting Monday with project team to discuss revised dates.
804347 | MS #3 - 30% Component Inspection | 248072 | 2025-08-21 | TBD | TBD
805203 | MS #4 - 10% Delivery | 29031 | 2025-08-22 | TBD | TBD
805207 | MS #4 - 10% Delivery | 75234 | 2025-08-22 | TBD | TBD
805306 | MS #3 - 20% Electrical Rough-In | 58059 | 2025-08-29 | TBD | TBD
805308 | MS #2 - 20% Superstructure | 58059 | 2025-09-01 | TBD | TBD
805049 | Monthly Progresss #13 | 56677 | 2025-09-01 | TBD | TBD
805328 | MS #2 - 30% PDR | 271168 | 2025-09-03 | TBD | TBD
804772 | MS #1 - 100% Delivery | 1912082 | 2025-09-05 | TBD | TBD
805132 | Monthly Progresss #12 | 93500 | 2025-09-09 | TBD | TBD
804874 | MS #3 - 25% Delivery | 100727 | 2025-09-09 | TBD | TBD
805287 | 10% Remaining Vehicle Cost | 119979 | 2025-09-11 | TBD | TBD
805184 | MS #4 - 10% Delivery | 60806 | 2025-09-12 | TBD | TBD
805308 | MS #3 - 20% Electrical Rough-in | 58059 | 2025-09-15 | TBD | TBD
805309 | MS #2 - 20% Superstructure | 58059 | 2025-09-15 | TBD | TBD
804540 | Delivery / Acceptance | 120786 | 2025-09-15 | TBD | TBD
804541 | Delivery / Acceptance | 120786 | 2025-09-15 | TBD | TBD
804264 | MS #3 - 10% Superstructure | 57600 | 2025-09-16 | TBD | TBD
804391 | MS #2 - 25% CDR | 143700 | 2025-09-17 | TBD | TBD
804347 | MS #4 - 20% Acceptance | 240575 | 2025-09-17 | TBD | TBD
805472 | MS #3 - 30% CDR | 69600 | 2025-09-17 | TBD | TBD
805314 | MS #3 - 25% CDR | 147662 | 2025-09-23 | TBD | TBD | [7 empty] | ME starting 10/27
805197 | MS #11 - Monthly Progress #7 | 67000 | 2025-09-25 | TBD | TBD
805337 | MS #3 - 30% Exposed Components Inspection | 248072 | 2025-09-25 | TBD | TBD
805319 | MS #4 - 10% Delivery | 60996 | 2025-09-25 | TBD | TBD
804656 | MS #4 - 20% Delivery | 289105 | 2025-09-26 | TBD | TBD
804893 | MS #1 - 100% Delivery | 915883 | 2025-09-26 | TBD | TBD
804273 | Event 7 - Final EMI Test | 50625 | 2025-09-26 | TBD | TBD
805476 | MS #3 - 30% Superstructure | 231416 | 2025-09-29 | TBD | TBD
805309 | MS #3 - 20% Electrical Rough-In | 58059 | 2025-09-29 | TBD | TBD
805228 | MS #1 - 100% Project Acceptance | 199500 | 2025-09-30 | TBD | TBD
805067 | Monthly Progress #6 | 147641 | 2025-09-30 | TBD | TBD
805049 | Monthly Progresss #14 | 28338 | 2025-10-01 | TBD | TBD
805306 | MS #2 - 20% Superstructure | 58059 | 2025-10-06 | TBD | TBD
804613 | MS #2 - 40% Shelter Frame | 247543 | 2025-10-10 | TBD | TBD
805288 | 10% Remaining Vehicle Cost | 119979 | 2025-10-10 | TBD | TBD
805477 | MS #3 - 30% SuperStructure | 215582 | 2025-10-13 | TBD | TBD
805079 | MS #2 - 30% Chassis Order | 413479 | 2025-10-15 | TBD | TBD
805306 | MS #4 - 10% Delivery | 29031 | 2025-10-17 | TBD | TBD
804273 | MS #8 - Delivery | 175000 | 2025-10-17 | TBD | TBD | [7 empty] | EMI Doors arriving beginning of May. Holds up Fabrication and EMi testing prior to assembly.
805157 | MS #3 - 30% SuperStructure | 231416 | 2025-10-20 | TBD | TBD
805517 | MS #2 - 30% PDR | 67410 | 2025-10-21 | TBD | TBD
805338 | MS #3 - 30% Exposed Components Inspection | 248072 | 2025-10-23 | TBD | TBD
805306 | MS #3 - 20% Electrical Rough-In | 58059 | 2025-10-24 | TBD | TBD
805198 | MS #1 - 100% Delivery | 987943 | 2025-10-24 | TBD | TBD
805642 | MS #2 - 30% PDR | 121213 | 2025-10-24 | TBD | TBD
805308 | MS #4 - 10% Delivery | 29031 | 2025-10-27 | TBD | TBD
805067 | Monthly Progress #6 | 73821 | 2025-10-30 | TBD | TBD
805186 | MS #2 - 20% PDR | 174849 | 2025-10-31 | TBD | TBD
804347 | MS #4 - 20% Acceptance | 240575 | 2025-11-01 | TBD | TBD
805310 | MS #2 - 20% SuperStructure | 58059 | 2025-11-03 | TBD | TBD
805135 | MS #1 - 100% Delivery | 1061807 | 2025-11-04 | TBD | TBD
805120 | MS #4 - 10% Delivery | 66076 | 2025-11-07 | TBD | TBD
805289 | 10% Remaining Vehicle Cost | 119979 | 2025-11-11 | TBD | TBD
805328 | MS #3 - 30% CDR | 271168 | 2025-11-12 | TBD | TBD
805309 | MS #4 - 10% Delivery | 29031 | 2025-11-14 | TBD | TBD
805121 | MS #2 - 30% PDR | 185825 | 2025-11-15 | TBD | TBD
805310 | MS #3 - 20% Electrical Rough In | 58059 | 2025-11-17 | TBD | TBD
805331 | MS #3 - 20% Superstructure | 173189 | 2025-11-19 | TBD | TBD
804886 | MS #3 - 25% Delivery | 247224 | 2025-11-21 | TBD | TBD
804264 | MS #4 - 10% Shipment | 57600 | 2025-11-27 | TBD | TBD
805326 | MS #2 - 50% Delivery | 188070 | 2025-11-28 | TBD | TBD
805355 | MS #1 - 100% on Delivery | 160785 | 2025-11-28 | TBD | TBD
805067 | Monthly Progress | 73821 | 2025-11-28 | TBD | TBD
804264 | MS #4 - 10% Delivery | 38641 | 2025-11-29 | TBD | TBD
805347 | Phase 4 Technical Data Package | 176629 | 2025-12-10 | TBD | TBD
805290 | 10% Remaining Vehicle Cost | 119979 | 2025-12-11 | TBD | TBD
805307 | MS #4 - 10% Delivery | 29031 | 2025-12-12 | TBD | TBD
804881 | MS #4 - 10% Delivery | 108681 | 2025-12-14 | TBD | TBD
805351 | MS #1 - 100% on Delivery | 1133307 | 2025-12-14 | TBD | TBD
805337 | MS #4 - 20% on Acceptance | 240575 | 2025-12-16 | TBD | TBD
804684 | MS #4 - 10% Delivery | 181800 | 2025-12-31 | TBD | TBD
803267 | MS #4 - 10% Delivery | 122837 | 2025-12-31 | TBD | TBD
805143 | MS #2 - 50% Delivery | 62961 | 2025-12-31 | TBD | TBD | [7 empty] | Adjusted to forecast
805296 | MS #4 - Delivery | 140470 | 2026-03-31 | TBD | TBD | [7 empty] | can't enter this date because it isn't open.