## Sheet1
Location | Team | Project | Project Status | PM | Proj # | Contract Date | DPAS Rating | Chassis ETA | Stretch / Shorten / Gears | Payment Milestones | LLTs Ordered | ME Assigned | ME Design / Orders % | EE Assigned | EE Design / Orders % | ITE Assigned | IT Design / Orders % | NTC Design / Orders % | Fabrication Start | Assembly Start | Wrap | NTC Testing | QC START | QC DAYS | EXECUTIVE REVIEW | Ship | Delivery | Comments
Field | FSW | 800607_DC_WaterandSewer_Nycoil Replacment | MINOR ISSUE |  | 800607 | [20 empty] | 2025-04-30 | 2025-05-12 | Nycoil parts shipping by 4/30 for field install. ISSUE: Parts needed from Supply Chain
Libby |  | 804884_TX_TexasA&M-CC_Sprinter | MINOR ISSUE | Matt | 804884 | 2025-04-17 |  | Arrived | N/A | Delivery - 5/9/25 | Done | Jason Evans | 100% | Roger F | 100% | Cody R | 100% | 0% | N/A | in work | Done | 2025-05-01 | 2025-05-05 | 4 | TBD | 2025-05-09 | 2025-05-13 | ME CAD Complete. ISSUE: NTC Still working to complete
Libby |  | 804813_MD_VA_MVCs_Sprinter_05 | MINOR ISSUE | Marie | 804813 | 2025-03-25 |  | Arrived | N/A | Delivery - 4/24/25 | Done | Jason Evans | 100% | Roger F | 100% | Nick H | 100% | 100% | N/A | in work | Done | N/A | 2025-05-05 | 4 | 5/8/25 @ ? | 2025-05-09 | 2025-05-14 | Deliver to: Watertown, NY ISSUE: Electrical concerns (ADA, Level Pump)
CFalls | NH / MF | 804507_NM_Lockheed_RK53As0 | GOOD | Jason | 804507 | 2025-03-21 |  | N/A | N/A | Delivery - 5/5/25 | Done | Jack Dioszeghy | 100% | Martin J | 99% |  | 95% | 100% | Done | in work | Done | in work | in work | IN QC | 5/8/25 @ 1400 | 2025-05-12 | 2025-05-15 | handrail rework in progress - with ENG
CFalls | JC / BH | 804666_OK_OKC-PD_IC32As0 | GOOD | Shey | 804666 | 2025-02-06 |  | Arrived | N/A | Delivery - 5/9/25 | Done | Chance Morine | 100% | Nick S | 100% | Cody R | 100% | 100% | Done | in work |  | 2025-04-24 | 2025-05-05 | 5 |  | 2025-05-12 | 2025-05-16
CFalls | DM / AL | 804653_AL_ADS_USACE_IC34As4_03 | GOOD | Jason | 804653 | 2025-01-17 | DOC9 | Arrived | N/A | Delivery -5/19/25 | Done | Bryce Puchta | 100% | Martin J | 100% |  | 100% | 100% | Done | in work | in work | in work | 2025-05-05 | 8 |  | 2025-05-15 | 2025-05-19 | ECCV 8 - deliver to Nashville - pending approval of USACE.
Libby |  | 804815_MD_VA_MVCs_Sprinter_07 | GOOD | Marie | 804815 | 2025-03-25 |  | Arrived | N/A | Delivery - 4/24/25 | Done | Jason Evans | 100% | Roger F | 100% | Nick H | 100% | 100% | N/A | in work | Done | N/A | 2025-05-07 | 7 | 5/15/25 @ 0945 | 2025-05-16 | 2025-05-20 | Deliver to: Dallas, TX // Need van at wrap on morning of 13 May
CFalls | JC / BH | 804731_NC_Iredell County_IC34As4 | GOOD | Shey | 804731 | 2/15/2025 -1 |  | Arrived | Frame rail Fix | Delivery - 5/2/25 | Done | Bryce Puchta | 100% | Austin K | 100% | Scott B | 100% | 0% | Done | in work | Decals | 2025-05-05 | 2025-05-12 | 5 |  | 2025-05-19 | 2025-05-23 | Ceramic coating required after graphics. ME CAD complete.
Libby |  | 804916_TX_LegalAidOfNorthwestTexas_IC18 Upfit | GOOD | Matt | 804916 | 5/7/2025 PoP 1 - 5/31/25 |  | Arrived | N/A | Delivery -5/30/25 | Done | Jason Evans | 100% | Austin G | 100% | Nick H | 100% | 0% | N/A | in work | 2025-05-05 | N/A | 2025-05-12 | 7 | 5/20/25 @ 9:30am | 2025-05-21 | 2025-05-26 | ME CAD Complete. Need formal PoP exstension. Client is aware of the delay due to getting in for wrap
Libby |  | 804814_MD_VA_MVCs_Sprinter_06 | GOOD | Marie | 804814 | 2025-03-25 |  | Arrived | N/A | Delivery - 4/24/25 | Done | Jason Evans | 100% | Roger F | 100% | Nick H | 100% | 100% | N/A | in work | in work | N/A | 2025-05-14 | 8 | 5/21/25 @ 0830 | 2025-05-26 | 2025-05-30 | Deliver to: Chicago Heights, IL
CFalls | RS / NM | 804287_VA_ADS_WSMR_RK53As4 | GOOD | Jason | 804287 | 2025-04-25 |  | N/A | N/A | Delivery - 5/29/25 | Done | Jordan Boyenga | 100% | Alex R | 100% |  | 100% | 100% | Done | in work |  | in work | 2025-05-06 | 14 |  | 2025-05-26 | 2025-05-29 | UPDATE: Shore Power Change/Floor seam - delayed NTC.
Libby |  | 804816_MD_VA_MVCs_Sprinter_08 | GOOD | Marie | 804816 | 2025-03-25 |  | Arrived | N/A | Delivery - 4/24/25 | Done | Jason Evans | 100% | Roger F | 100% | Nick H | 100% | 100% | N/A | in work | in work | N/A | 2025-05-14 | 8 | 5/21/25 @ 0945 | 2025-05-26 | 2025-05-30 | Deliver to: Santa Cruz, CA
Libby |  | 804907_DC_EPA_WinnebagoNavion_MAM Upfit | GOOD | Marie | 804907 | 2025-04-15 |  | Arrived | N/A | Delivery - 5/30/25 | Done | Marcus Tokmak | 100% | Roger F | 100% |  | N/A | 0% | N/A | in work | Mag Decals | N/A | 2025-05-19 | 7 |  | 2025-05-28 | 2025-05-30 | EPA/ GSA inspection and drive away 28-29 May. ME CAD Complete Working on compiling all material before commiting to dates. Hoping to keep it in April
CFalls | DM / AL | 804654_AL_ADS_USACE_IC34As4_04 | MAJOR ISSUE | Jason | 804654 | 2025-01-17 | DOC9 | Arrived | N/A | Delivery - 6/2/25 | Done | Bryce Puchta | 100% | Martin J | 100% |  | 100% | 100% | Done | in work | Decals | 2025-05-15 | 2025-05-19 | 8 |  | 2025-05-29 | 2025-06-02 | ECCV 07 - deliver to Vicksburg. ISSUE: E-Chain bracket Needed for Production to Continue ~ 4 weeks
CFalls | RH / CO | 804503_MD_DEVCOM_TCVMAX_01 | MAJOR ISSUE | Jason | 804503 | 2025-04-17 |  | Arrived | Done | Delivery - 6/6/25 | Done | Will Busching | 100% | Calvin C | 100% |  | 100% | 0% | Done | in work | N/A | 2025-05-12 | 2025-05-19 | 9 |  | 2025-05-30 | 2025-06-06 | ISSUE: ENG, subsequently parts, pushing production timelines.
CFalls | FSW | 805268_MT_LewisClarkPublicHealth_Retrofit | MINOR ISSUE |  | 805268 | 7/30/25 - 1 | [15 empty] | NA | 2025-04-25 | 25 |  | 2025-05-30 | 2025-06-02 | Sprinter Van. Needs space. Bldg 5. April 1st. ISSUE: Large Electrical Upfit?
CFalls | RH / CO | 804484_TX_TMobile_SatCOLT_02 | GOOD | Shean | 804484 | 2024-02-13 |  | Arrived | N/A | Delivery -6/3/25 | Done | Trevor Jobst | 100% | Nick S | 100% | Nick H | 100% | 100% | Done | in work | N/A | 2025-05-23 | 2025-05-26 | 4 | 5/28/25 @? | 2025-05-30 | 2025-06-03 | AVL ESD mid-May
CFalls | JN / NM | 804018_TN_TennDeptOfHealth_D24As2_01 | GOOD | Shey | 804018 | 2025-06-30 |  | N/A |  | Delivery - 6/6/25 | Done | Chance Morine | 100% | Calvin C | 100% | Nick H | 100% | 0% | Done | in work | Decals | 2025-05-19 | 2025-05-26 | 5 |  | 2025-06-02 | 2025-06-06 | ME CAD Complete. FAB material issues
CFalls | JN / NM | 805343_TN_TennDeptOfHealth_D24As2_02 | GOOD | Shey | 805343 | 2025-06-30 |  | N/A |  | Delivery - 6/6/25 | Done | Bryce Puchta | 100% | Calvin C | 100% | Nick H | 100% | 0% | Done | in work | Decals | 2025-05-19 | 2025-05-26 | 5 |  | 2025-06-02 | 2025-06-06 | ME CAD Complete. Awt material ETA 2/7/25. Fab completion ETIC 2/6/25
CFalls | NH / MF | 804928_IA_IowaDAS_IC32As2 | MINOR ISSUE | Marie | 804928 | 2025-07-01 |  | Arrived | N/A | Delivery - 7/4/25 | Done | Ryan Van Marel | 100% | Andrew B | 100% | Werner S | 82% | 0% | Done | in work | 2025-05-19 | 2025-05-27 | 2025-05-30 | 9 | 6/5/25 @ ? | 2025-06-12 | 2025-06-16 | Customer visit 10-11 June Contract date not flexible; ME CAD Complete. ISSUE: IT concern/Dinete
CFalls | RS / NM | 805206_CA_Edwards AFB_CST-TOW_02 | GOOD | Shelden | 805206 | 2025-09-10 | DOC9 | N/A |  | Superstructure - 3/24/25 Delivery - 6/20/25 | Done | Sean McGee | 100% | Finn S | 100% | Cody R | 100% | 0% | Done | in work |  | 2025-06-02 | 2025-06-09 | 5 |  | 2025-06-16 | 2025-06-20 | ME CAD complete
Field | FSW | 800582_NY_NiagaraCountySheriff (IT Refresh) | GOOD |  | 800582 | 2025-12-23 | [15 empty] | 2025-06-02 |  | IN QC |  | 2025-06-16 | 2025-06-25
CFalls | RH / CO | 804545_CA_Edwards AFB_CST-TOW_01 | GOOD | Shelden | 804545 | 2025-09-10 | DOC9 | N/A | N/A | Delivery - 6/20/25 | Done | Sean McGee | 100% | Finn S | 100% | Cody R | 100% | 0% | Done | in work |  | 2025-06-02 | 2025-06-09 | 5 |  | 2025-06-16 | 2025-06-20 | ME wind fairings released
CFalls | JC / BH | 804862_MD_FEMA_MCOV_20 | GOOD | Marie | 804862 | 2025-07-19 |  | Arrived |  | Electrical Rough-in - 5/2/25 Delivery - 6/20/25 | Done | John Phillips | 100% | Martin J | 100% | Cody R | 100% | N/A | Done | in work | Decals | N/A | 2025-06-09 | 5 |  | 2025-06-16 | 2025-06-20 | ME CAD Released, Executed 12/20
Libby |  | 806503_PA_KRATOS_PTSuspension_EU1 | MINOR ISSUE | Brian | 806503 | 2021-03-21 |  | N/A | N/A | Assembly - 6/5/25 Testing - 6/6/25 Delivery - 6/23/25 | Done | [5 empty] | N/A | N/A | in work | 2025-05-12 | N/A | N/A | 2025-05-26 | 15 |  | 2025-06-16 | 2025-06-23 | Milestones need to move to coincide with Monthly billing. Paint issues are putting Assembly start at risk.
Libby |  | 804542_AL_GaN_MOSAIC_FSS | GOOD | Brad | 804542 |  | DOA2 | N/A | N/A | Delivery - 6/24/25 | Done | Jeff Gaddy |  | Roger F | 100% |  |  |  | Done | In work | N/A | 2025-04-22 | 2025-05-27 | 8 | 2025-06-06 | 2025-06-17 | 2025-06-24 | 4/21-25 FAT
CFalls | JC / BH | 805214_MD_FEMA_MCOV_21 | GOOD | Marie | 805214 | 2025-07-19 |  | Arrived |  | Superstructure - 4/21/25 Electrical Rough-in - 5/9/25 Delivery - 6/27/25 | Done | Chance Morine | 100% | Martin J | 100% | Cody R | 100% | N/A | Done | in work | Decals | N/A | 2025-06-16 | 5 |  | 2025-06-23 | 2025-06-27 | ME CAD Released, Executed 12/20
CFalls | JN / NM | 805344_TN_TennDeptOfHealth_D24As2_03 | GOOD | Shey | 805344 | 2025-06-30 |  | N/A |  | Delivery - 6/27/25 | Done | Bryce Puchta | 100% | Calvin C | 100% | Nick H | 100% | 0% | Done | in work | Decals | 2025-06-09 | 2025-06-16 | 5 |  | 2025-06-23 | 2025-06-27 | ME CAD complete
CFalls | JN / NM | 805345_TN_TennDeptOfHealth_D24As2_04 | GOOD | Shey | 805345 | 2025-06-30 |  | N/A |  | Delivery - 6/27/25 | Done | Bryce Puchta | 100% | Calvin C | 100% | Nick H | 100% | 0% | Done | in work | Decals | 2025-06-09 | 2025-06-16 | 5 |  | 2025-06-23 | 2025-06-27 | ME CAD Complete
CFalls | DM / AL | 804655_AL_ADS_USACE_IC34As4_05 | MINOR ISSUE | Jason | 804655 | 2025-01-17 | DOC9 | Arrived | N/A | Delivery - 6/27/25 | Done | Bryce Puchta | 100% | Martin J | 100% |  | 100% | 100% | Done | in work | Decals | 2025-06-09 | 2025-06-16 | 5 |  | 2025-06-23 | 2025-06-27 | ISSUE: slideout fix timeline will dictate schedule.
CFalls | RS / NM | 804621_NM_DVS_IC22As0 | GOOD | Shey | 804621 | 2025-06-30 |  | Arrived | AWD | Delivery - 5/16/25 | Done | Chance Morine | 100% | Austin G | 100% | Link G | 95% | 100% | Done | in work | Wrap | 2025-04-21 | 2025-05-12 | 33 |  | 2025-06-26 | 2025-06-30 | 4/21/25: EZ Track upfit in IN. ERTB early May.
Libby |  | 804817_MD_VA_MVCs_IC33 Winnebago_01 | MINOR ISSUE | Marie | 804817 | 3/25/25 - 1 |  | Arrived | N/A | Delivery - 5/19/22 | Done | John Phillips | 100% | Nick S | 100% | Nick H | 100% | 100% | N/A | in work | Done | N/A | 2025-06-09 | 15 |  | 2025-06-30 | 2025-06-30 | ME CAD complete; VSAT swap, Telematics cw, Starlink install 5/5/25 ISSUE: FRP Not bought/issued for this build
Libby |  | 804819_MD_VA_MVCs_IC33 Winnebago_03 | MINOR ISSUE | Marie | 804819 | 2025-03-25 |  | Arrived | N/A | Delivery - 5/19/23 | Done | John Phillips | 100% | Nick S | 100% | Nick H | 100% | 100% | N/A | in work | Done | N/A | 2025-06-09 | 15 |  | 2025-06-30 | 2025-06-30 | ME CAD complete; VSAT swap, Telematics cw, Starlink install 5/5/25 ISSUE: FRP Not bought/issued for this build
Libby |  | 804818_MD_VA_MVCs_IC33 Winnebago_02 | GOOD | Marie | 804818 | 2025-03-25 |  | Arrived | N/A | Delivery - 5/19/24 | Done | John Phillips | 100% | Nick S | 100% | Nick H | 100% | 100% | N/A | in work | Done | N/A | 2025-06-16 | 10 |  | 2025-06-30 | 2025-06-30 | ME CAD complete; VSAT swap, Telematics cw, Starlink install 5/5/25
Libby |  | 804821_MD_VA_MVCs_IC33 Winnebago_05 | GOOD | Marie | 804821 | 2025-03-25 |  | Arrived | N/A | Delivery - 5/19/25 | Done | John Phillips | 100% | Nick S | 100% |  | 100% | 100% | N/A | in work | in work | N/A | 2025-06-16 | 10 |  | 2025-06-30 | 2025-06-30 | ME CAD complete; VSAT swap, Telematics cw, Starlink install 5/5/25
Libby |  | 804820_MD_VA_MVCs_IC33 Winnebago_04 | GOOD | Marie | 804820 | 2025-03-25 |  | Arrived | N/A | Delivery - 5/19/25 | Done | John Phillips | 100% | Nick S | 100% |  | 100% | 100% | N/A | in work | Done | N/A | 2025-06-23 | 5 |  | 2025-06-30 | 2025-06-30 | ME CAD complete; VSAT swap, Telematics cw, Starlink install 5/5/25
Libby |  | 804822_MD_VA_MVCs_IC33 Winnebago_06 | GOOD | Marie | 804822 | 2025-03-25 |  | Arrived | N/A | Delivery - 5/19/25 | Done | John Phillips | 100% | Nick S | 100% |  | 100% | 100% | N/A | in work | 5/8/25 - Wraphive | N/A | 2025-06-23 | 5 |  | 2025-06-30 | 2025-06-30 | ME CAD complete; VSAT swap, Telematics cw, Starlink install 5/5/25
Libby |  | 805040_CO_SierraNevadaCorp_Sprinter | GOOD | Matt | 805040 | 2025-07-13 |  | Arrived | N/A | Delivery - 7/10/25 | Done | Jason Evans | 100% | Roger F | 100% | Cody R | 100% | 0% | N/A | In Work | N/A | N/A | 2025-06-13 | 11 |  | 2025-06-30 | 2025-07-03 | May move left - need NTC date
CFalls | RS / NM | 804450_GA_GTRI Project A_CST-TOW | MINOR ISSUE | Shelden | 804450 | 2025-07-08 |  | N/A | N/A | Delivery - 7/7/25 | Done | Sean McGee | 100% | Nick S | 100% |  | 100% | 0% | Done | 2025-04-28 |  | 2025-06-16 | 2025-06-23 | 7 |  | 2025-07-02 | 2025-07-07 | ME Fully CAD Released. Parts availability will hold up assembly start. ISSUE: Have we not started assembly on this yet? Will be as risk for shipment if we dont start ASAP. PARTS NEED ORDERED.
CFalls | NH / MF | 805304_TX_Rohde&Schwarz_SOV | MAJOR ISSUE | Shey | 805304 | 2025-08-15 | DOC9 | Mar 2025 | lift? | Delivery - 7/11/25 |  |  | 100% | Austin K | 100% | Cody R/Werner S | 38% | 0% | Done | in work |  | 2025-06-18 | 2025-06-25 | 8 |  | 2025-07-07 | 2025-07-11 | Full ME CAD released. Shigo to assess schedule. ISSUE: Parts needed for successful milestone completion. If we order parts ASAP, we have a chance to ship on time. Needs to test new Power Supply, may need addt ~ 1-week push.
CFalls | NH / MF | 805319_TX_Rohde&Schwarz_SOV | MAJOR ISSUE | Chris Peek | 805319 | 2025-09-25 | DOC9 | Arrived | gears/brakes? | CDR - 3/28/25 Delivery - 8/29/25 |  | Alex Herbst | 100% | Austin K | 75% | Cody R/Werner S | 0% | 0% | 2025-05-05 | 2025-06-16 |  | 2025-06-27 | 2025-07-07 | 5 |  | 2025-07-14 | 2025-07-18 | ME full CAD released. ISSUE: Even if FAB starts on time, this gives Assembly ~2 weeks to complete. We will NOT ship this on time, best case scenario.
Field | FSW | 803913_AL_GAN-REDSTONE_ECTM_01 |  |  | 803913 | 2025-05-02 | [15 empty] | 2025-07-10 |  | IN QC |  | 2025-07-23 | 2025-07-30
Libby |  | 806504_PA_KRATOS_PTSuspension_EU2 | GOOD | Brian | 806504 | 2021-03-21 | DX | N/A | N/A | Assembly - 6/6/25 Testing - 6/20/25 Delivery -8/11/25 | [6 empty] | N/A | N/A | in work | 2025-05-26 | N/A | N/A | 2025-06-16 | 35 |  | 2025-08-04 | 2025-08-11 | Kratos indicated verbally on 3-19-25 that expectation for EU-2 delivery would be November 2025 instead of August. May impact Testing and Delivery milestones.
CFalls | NH / MF | 805184_TX_Rohde&Schwarz_SOV | MAJOR ISSUE | Shey | 805184 | 2025-09-25 | DOC9 | Arrived | gears/brakes? | CDR - 3/28/25 Delivery -8/29/25 |  | Alex Herbst | 100% | Austin K | 75% | Cody R/Werner S | 38% | 0% | 2025-05-12 | 2025-06-23 |  | 2025-07-28 | 2025-08-04 | 5 |  | 2025-08-11 | 2025-08-15 | Full CAD comp 4/25/25 ISSUE: FAB must start on time, if not before to gain some weeks of assembly back, currently sitting at only 4-5 weeks production time at best case scenario. This is at risk for not leaving on time.
CFalls | RS / NM | 805207_CA_Edwards AFB_CST-TOW_03 | GOOD | Shelden | 805207 | 2025-09-10 | DOC9 | N/A |  | Superstructure - 6/2/25 Delivery - 8/22/25 | Done | Sean McGee | 100% | Finn S | 100% | Cody R | 100% | 0% | in work | 2025-06-02 |  | 2025-08-04 | 2025-08-11 | 5 |  | 2025-08-18 | 2025-08-22 | Full ME CAD released
CFalls | JC / BH | 805203_MD_FEMA_MCOV_22 | GOOD | Marie | 805203 | 2025-11-06 |  | Arrived |  | Superstructure - 6/16/25 Electrical Rough-in - 7/4/25 Delivery - 8/22/25 | Done | Chance Morine | 100% | Martin J | 100% | Cody R | 100% | N/A | 2025-05-05 | 2025-06-16 |  | N/A | 2025-08-11 | 5 |  | 2025-08-18 | 2025-08-22 | ME CAD Released, Executed 12/20
Libby |  | 804540_AL_GaN_MOSAIC_TM_01 | GOOD | Brad | 804540 |  | DOA2 | N/A | N/A | Delivery - 8/29/25 | Done | Jeff Gaddy | 100% | Roger F | 100% |  | 100% |  | Done | 2025-05-27 | N/A | 2025-06-18 | 2025-07-30 | 8 | 2025-08-11 | 2025-08-22 | 2025-08-29
Libby |  | 804541_AL_GaN_MOSAIC_TM_02 | GOOD | Brad | 804541 |  | DOA2 | N/A | N/A | Delivery - 8/29/25 | Done | Jeff Gaddy |  | Roger F | 100% | Cody R | 100% | in work | Done | 2025-05-27 | N/A | 2025-06-18 | 2025-07-30 | 8 | 2025-08-11 | 2025-08-22 | 2025-08-29
Libby |  | 805201_FL_FlorindaForestService_RK53As4_01 |  | Matt | 805201 | 2025-09-30 |  | July 2025 |  | Monthly | in work | Bryce Puchta | 0% | Andrew B | 70% |  | 0% | 0% | 2025-05-12 | 2025-06-30 | Partial Wrap | 2025-08-04 | 2025-08-18 | 10 |  | 2025-09-01 | 2025-09-05 | ME Full CAD Release 5/30/25 (Excuted X 4/25 & DWg commit X 5/2)
Libby |  | 804772_WA_VA_IC45 Prevost |  | Matt | 804772 | 12/31/2025 -1 |  | Arrived | N/A | Delivery - 9/5/25 |  | Jason Evans | 30% | Andrew B | 0% |  | 38% | 0% | N/A | 2025-06-16 | Full Wrap | 2025-08-11 | 2025-08-25 | 5 |  | 2025-09-01 | 2025-09-05 | All esctions executed 5/1/25, ME Full CAD Release 5/16/25
Libby |  | 805673_CA_JT4_IC14As0 KSU_07 |  | Ashley | 805673 | 2026-09-30 | DOC9 | Mar 2025 | Gears | Monthly |  | Chaffin Ross | 100% | Roger F | 100% | Cody R | 95% | 0% | 2025-06-16 | 2025-06-23 | N/A | N/A | 2025-09-01 | 5 |  | 2025-09-08 | 2025-09-12 | 4/30/25: REPLACED FTS 1 WITH KSU 7. Colter to Confirm BID Hours.
CFalls | DM / AL | 804874_NM_RobertsTruck_BernalilloCo_IC26As0_03 | MINOR ISSUE | Shey | 804874 | 2025-09-09 |  | Arrived |  | Delivery - 9/12/25 |  | Chaffin Ross | 0% | Calvin C | 0% | Cody R | 0% | 0% | 2025-04-21 | 2025-06-09 |  | 2025-08-25 | 2025-09-01 | 5 |  | 2025-09-08 | 2025-09-12 | ME Full CAD Release 5/9/25. (X CAD & executed 4/11)
CFalls | RH / CO | 805049_UT_Hill AFB_TCVMax TCV-UT1 | GOOD | Ashley | 805049 | 2025-08-15 | DOC9 | Arrived |  | Monthly Progress - Delivery - 9/19/25 | Done | Savannah Drey | 100% | Alex R | 47% | Link G | 5% | 0% | Done | 2025-06-01 |  | 2025-09-01 | 2025-09-08 | 5 |  | 2025-09-15 | 2025-09-19 | ME CAD Fully Released.
CFalls | RS / NM | 804347_DC_FEMA_MLOU_RK42As3_01 |  | Marie | 804347 | 2025-09-17 |  | N/A |  | Component Inspection - 8/8/25 Acceptance - 9/26/25 | Done | Trevor Jobst | 25% | Finn S | 0% | Link G | 0% | 0% | 2025-04-07 | 2025-06-02 | 9/1-2/25 | 2025-09-08 | 2025-09-15 | 5 |  | 2025-09-22 | 2025-09-26 | ME Full CAD complete Awt axles ETA mid-May
Libby |  | 805297_FL_FloridaForestService_RK53As4_02 |  | Matt | 805297 | 2025-09-30 |  | July 2025 |  | Monthly | in work | Bryce Puchta | 0% | Andrew B | 35% |  | 0% | 0% | 2025-05-26 | 2025-06-21 | Partial Wrap | 2025-09-01 | 2025-09-08 | 10 |  | 2025-09-22 | 2025-09-26 | ME Full CAD Release 5/30/25 (Excute & Release X 4/25)
Libby |  | 805674_CA_JT4_IC14As0 LV_01 |  | Ashley | 805674 | 2026-09-30 | DOC9 | Mar 2025 |  | Monthly |  | Chaffin Ross | 0% | Roger F | 0% | Cody R | 0% | 0% | 2025-06-30 | 2025-07-07 | N/A | N/A | 2025-09-15 | 5 |  | 2025-09-22 | 2025-09-26 | 4/30/25: REPLACED FTS 2 WITH LV 1. Colter to Confirm BID Hours.
CFalls | DM / AL | 804656_AL_ADS_USACE_IC34As4_06 | MINOR ISSUE | Jason | 804656 | 2025-01-17 | DOC9 | Arrived | N/A | Superstructure - 4/11/25 Electrical Rough-in - 5/9/25 Delivery - 9/26/25 | Done | Bryce Puchta | 100% | Martin J | 100% |  | 100% | 100% | Done | 2025-04-21 | Decals | 2025-09-08 | 2025-09-15 | 5 |  | 2025-09-22 | 2025-09-26 | current schedule informs early Aug ship.
CFalls | JN / NM | 804893_CA_DLA_ResponderR32As4 |  | Shey | 804893 | 2025-09-08 |  | N/A |  | Delivery - 9/26/25 |  | Ryan Van Marel | 27% | Nick S | 52% | Scott B | 0% | 0% | 2025-04-21 | 2025-06-16 |  | 2025-09-08 | 2025-09-15 | 5 |  | 2025-09-22 | 2025-09-26 | ME Full CAD Release 5/16/25, LL dropped, 4/21 fab start risk due to FEA analysis
CFalls | JC / BH | 805306_MD_FEMA_MCOV_23 |  | Marie | 805306 | 2025-11-06 |  | Arrived | N/A | Superstructure - 8/11/25 Electrical - 8/29/25 Delivery - 10/17/25 | Done | Chance Morine | 100% | Martin J | 100% |  | 100% | 100% | 2025-06-30 | 2025-08-11 |  | N/A | 2025-10-06 | 5 |  | 2025-10-13 | 2025-10-17 | ME CAD Released, Executed 12/20
CFalls | RH / CO | 804273_TX_Lockheed_MUSTANG_01 | MINOR ISSUE | Chris Peek / Ashley | 804273 | 2025-08-09 | DXA7 | Arrived |  | Elec Rough-in - 6/13/25 Mast Installed - 7/31/25 Final EMI test - 9/26/25 | in work | Will Busching | 51% | Calvin C | 25% | Cody R | 95% | 0% | in work | 2025-05-26 |  | 2025-10-01 | 2025-10-06 | 5 |  | 2025-10-13 | 2025-10-17 | full ME CAD Commit 5/16/25 (X executed & released 3/3, ACE executed ). EMI doors ETA early May
CFalls | NH / MF | 805253_UT_Hill AFB_IC14As0 FTS-UT2 | MAJOR ISSUE | Ashley | 805253 | 2025-10-09 | DOC9 | Arrived |  | Monthly Delivery - 8/8/25 |  | Theo Kourkoutis | 0% | Alex R | 0% | Link G | 0% | 0% | 2025-06-30 | 2025-08-11 |  | 2025-09-29 | 2025-10-06 | 5 |  | 2025-10-13 | 2025-10-17 | At Risk! Excessive client data racks will overload F550 chassis quoted
CFalls | JN / NM | 805198_AL_AEMA_IC26As2 |  | Shey | 805198 | 2025-08-22 |  | Ordered, ETA? |  | Delivery - |  | Marcus Tokmak | 100% | Finn S | 90% | Scott B | 0% | 0% | in work | 2025-06-09 |  | 2025-10-06 | 2025-10-13 | 5 |  | 2025-10-20 | 2025-10-24 | ME CAD fully released
CFalls | RS / NM | 805336_DC_FEMA_MLOU_RK42As3_02 |  | Marie | 805336 | 2025-11-01 |  | N/A |  | Component Inspection - 9/5/25 Acceptance -10/31/25 |  | Trevor Jobst | 25% | Finn S | 0% | Link G | 0% | 0% | 2025-05-12 | 2025-07-07 | 9/20-21/25 | 2025-10-12 | 2025-10-20 | 5 |  | 2025-10-27 | 2025-10-31 | ME Full CAD Complete
Libby |  | 805347_AL_RedstoneTestCenter_ISO20_ECP Lift Container_01 |  | Sam | 805347 | 2024-12-23 | DX | N/A | N/A | MPP Manufacturing Kick Off - 3/3/25 Superstructure - 4/11/25 |  |  |  | Roger F |  |  |  |  | Done | 2025-05-19 | N/A |  | 2025-09-29 | 20 |  | 2025-10-27 | 2025-11-05
Libby |  | 805348_AL_RedstoneTestCenter_ISO20_ECP Lift Container_02 |  | Sam | 805348 | 2024-12-23 | DX | N/A | N/A | See 805347 |  |  |  | Roger F |  |  |  |  | in work | 2025-05-19 | N/A |  | 2025-09-29 | 20 |  | 2025-10-27 | 2025-11-05
Libby |  | 805349_AL_RedstoneTestCenter_ISO20_ECP Lift Container_03 |  | Sam | 805349 | 2024-12-23 | DX | N/A | N/A | See 805347 |  |  |  | Roger F |  |  |  |  | in work | 2025-05-19 | N/A |  | 2025-09-29 | 20 |  | 2025-10-27 | 2025-11-05
Libby |  | 805132_CA_JT4_IC14As0 KSU_01 | GOOD | Ashley | 805132 | 2025-09-09 | DOC9 | Arrived | Gears Done | Monthly | Done | Chaffin Ross | 100% | Roger F | 100% | Cody R | 95% | 0% | Done | in work | N/A | N/A | 2025-06-16 | 100 |  | 2025-11-03 | 2025-11-10 | ME CAD Complete. HVAC ETA 20--24 weeks, end of August.
Libby |  | 805120_CA_SanDiegoCounty_IC26As1 |  | Shey | 805120 | 2025-09-15 |  | working |  | PDR - 5/13/25 CDR - 6/2/25 Delivery - 11/7/25 |  | Luke Zamoyski | 30% | Parker R | 0% | Scott B | 0% | 0% | 2025-07-28 | 2025-08-11 |  | 2025-10-22 | 2025-10-27 | 5 |  | 2025-11-03 | 2025-11-07 | Full CAD release commit 7/7/25
Libby |  | 805287_CA_JT4_IC14As0 KSU_02 | GOOD | Ashley | 805287 | 2025-09-09 | DOC9 | arrived | Gears | Monthly | Done | Chaffin Ross | 100% | Roger F | 100% | Cody R | 95% | 0% | Done | 2025-04-30 | N/A | N/A | 2025-06-30 | 95 |  | 2025-11-10 | 2025-11-14 | ME CAD Complete
Libby |  | 805288_CA_JT4_IC14As0 KSU_03 | GOOD | Ashley | 805288 | 2025-09-09 | DOC9 | arrived | Gears | Monthly | Done | Chaffin Ross | 100% | Roger F | 100% | Cody R | 95% | 0% | in work | 2025-05-07 | N/A | N/A | 2025-07-14 | 90 |  | 2025-11-17 | 2025-11-21 | ME CAD Complete
CFalls | JC / BH | 804886_OK_CherokeeNation_IC34As4 |  | Shey | 804886 | 2025-08-27 |  | Arrived |  | Superstructure -5/30/25 Delivery - 11/21/25 | Done | Trevor Jobst | 99% | Shea M | 40% | Scott B/Nick H | 63% | 0% | Done | 2025-06-09 |  | 2025-11-03 | 2025-11-10 | 5 |  | 2025-11-17 | 2025-11-21 | Freightliner Chassis. client approved Eaton Trans , ME CAD Released
CFalls | RH / CO | 805326_DC_CBP_OPR IOD_IC16As0 | GOOD | Ashley | 805326 | 2025-10-02 |  | Arrived |  | Delivery - |  | Chaffin Ross | 0% | Austin G | 20% | Link G | 0% | 0% | 2025-07-21 | 2025-09-01 |  | 2025-11-10 | 2025-11-17 | 5 |  | 2025-11-24 | 2025-11-28 | Full CAD Release commit 8/7/25
CFalls | RH / CO | 805197_AL_NorthropGrumman_TCVMAX |  | Rick | 805197 | 2025-09-30 |  | Arrived |  | Monthly - Delivery - 11/28/25 |  | Will Busching | 100% | Alex R | 100% | Link G | 0% | 0% | 2025-07-14 | 2025-08-25 |  | 2025-11-10 | 2025-11-17 | 5 |  | 2025-11-24 | 2025-11-28 | Full CAD release 7/14/25
Libby |  | 804264_SC_DSIT_IC18As0 |  | Shelden | 804264 | 2025-11-27 |  | Arrived |  | CAD Package - Superstructure - 9/15/25 Delivery - 11/28/25 |  | Brandon Bickel | 0% | Austin G | 0% |  | 0% | 0% | 2025-09-01 | 2025-09-15 |  |  | 2025-11-17 | 5 |  | 2025-11-24 | 2025-11-28 | Full CAD release 8/25/24
Libby |  | 805355_ID_MoPOC_Van_19 |  | Matt | 805355 | 2025-12-27 |  |  |  | Delivery - |  |  |  | David H | [8 empty] | 2025-11-17 | 5 |  | 2025-11-24
Libby |  | 805289_CA_JT4_IC14As0 KSU_04 | GOOD | Ashley | 805289 | 2025-09-09 | DOC9 | arrived | Gears | Monthly | Done | Chaffin Ross | 100% | David H | 100% | Cody R | 95% | 0% | 2025-04-23 | 2025-05-12 | N/A | N/A | 2025-07-28 | 90 |  | 2025-12-01 | 2025-12-05 | ME Full CAD Releasd
Libby |  | 804881_NM_BlueHalo AFRL_IC16As0 | GOOD | Brad | 804881 | 2025-12-14 |  | Arrived |  | CDR - 5/9/25 Delivery - 12/3/25 |  | Sean McGee | 0% | Parker R | 0% |  | 0% | 0% | 2025-06-09 | 2025-07-28 | N/A | 2025-11-10 | 2025-11-24 | 5 |  | 2025-12-01 | 2025-12-03 | Awaiting ME input. Full ME CAD Release commit 6/15/25
Libby |  | 805577_ID_VA_MoPOC_Van_20 |  | Matt | 805577 | 2025-12-26 |  |  |  | Delivery - |  |  |  | Andrew B |  |  |  |  | n/a | 2025-10-20 |  |  | 2025-11-24 | 5 |  | 2025-12-01
Libby |  | 805290_CA_JT4_IC14As0 KSU_05 | GOOD | Ashley | 805290 | 2025-09-09 | DOC9 | arrived | Gears | Monthly | Done | Chaffin Ross | 100% | Roger F | 100% | Cody R | 95% | 0% | 2025-05-07 | 2025-05-26 | N/A | N/A | 2025-08-11 | 85 |  | 2025-12-08 | 2025-12-12 | ME Full CAD Releasd
CFalls | JC / BH | 805307_MD_FEMA_MCOV_24 |  | Marie | 805307 | 2025-11-06 |  | Arrived | N/A | Superstructure - 10/6/25 Electrical - 10/24/25 Delivery -12/12/25 | Done | Chance Morine | 100% | Martin J | 100% |  | 100% | 100% | 2025-08-25 | 2025-10-06 |  | N/A | 2025-12-01 | 5 |  | 2025-12-08 | 2025-12-12 | ME CAD Released, Executed 12/20
CFalls | NH / MF | 805067_TX_RioGrandeValley 911_IC34As4 |  | Jason | 805067 | 2026-02-13 |  | Aug 2025 |  | Monthly - PDR - 5/7/25 Delivery - 12/12/25 |  | Trevor Jobst | 5% | Parker R | 0% |  | 0% | 0% | 2025-06-16 | 2025-08-11 |  | 2025-11-24 | 2025-12-01 | 5 |  | 2025-12-08 | 2025-12-12 | ME Full CAD release commit 7/4/25
Libby |  | 805157_DC_Senate SAA_IC22As0_01 |  | Matt | 805157 | 2025-12-30 |  | working |  | CDR - 6/30/25 Superstructure-10/20/25 Delivery - 12/12/25 |  | Jack Dioszeghy | 0% | Finn S | 0% |  | 0% | 0% | 2025-07-21 | 804887 | N/A | 2025-11-17 | 2025-12-01 | 5 |  | 2025-12-08 | 2025-12-12 | ME CAD Fully released Commit 7/21/25
Libby |  | 805291_CA_JT4_IC14As0 KSU_06 | GOOD | Ashley | 805291 | 2025-09-09 | DOC9 | Mar 2025 | Gears | Monthly | Done | Chaffin Ross | 100% | Roger F | 100% | Cody R | 95% | 0% | 2025-06-02 | 2025-06-30 | N/A | NA | 2025-08-25 | 80 |  | 2025-12-15 | 2025-12-19 | ME Full CAD Releasd
CFalls | JN / NM | 804613_CA_SanDiego ICAC_IC20As0 |  | Shey | 804613 | 2025-12-28 |  | Arrived |  | Superstructure - 10/10/25 Delivery - 12/19/25 |  | Luke Zamoyski | 0% | Austin G | 0% |  | 0% | 0% | 2025-08-25 | 2025-10-06 |  | 2025-12-01 | 2025-12-08 | 5 |  | 2025-12-15 | 2025-12-19 | Full CAD release 9/15/25
CFalls | NH / MF | 805143_GA_GTRI_Tacoma_01 |  | Shelden | 805143 | ASAP |  |  |  | Delivery - |  |  |  | Roger F |  |  |  |  | n/a | 2025-11-24 |  | n/a | 2025-12-08 | 5 |  | 2025-12-15
CFalls | DM / AL | 803267_CA_VandenbergAFB_IC24As0_Custom01 |  | Ashley | 803267 | 7/31/2025 - 3 |  | Arrived | N/A | Delivery - 12/31/25 | Done | Luke Zamoyski | 100% | Martin J | 100% | Nick H | 100% | 50% | Done | in work | N/A | 2025-12-01 | 2025-12-15 | 5 |  | 2025-12-22 | 2025-12-31 | ME working microwave antenna/mast solution.
CFalls | DM / AL | 804684_CA_Vandenberg Space Force Base_D16 |  | Ashley | 804684 | 7/31/2025 - 3 |  | N/A | N/A | Delivery - 12/31/25 | Done | Jordan Boyenga | 100% | Martin J | 100% | Nick H | 0% | 0% | Done | in work | N/A | 2025-12-01 | 2025-12-15 | 5 |  | 2025-12-22 | 2025-12-31 | ME CAD Complete. Need lift and lay repainted by vendor
CFalls | RH / CO | 805440_FL_EglinAFB_CST-DRV_01 |  | Ashley | 805440 |  |  | N/A |  |  |  | Jack Dioszeghy | 0% | Alex R | 0% |  | 0% | 0% | 2025-09-29 | 2025-11-10 |  | 2025-11-08 | 2025-12-15 | 5 |  | 2025-12-22 | 2025-12-31 | ME CAD Fully released commit 10/15/25
CFalls | RH / CO | 805581_FL_EglinAFB_CST-DRV_02 |  | Ashley | 805581 |  |  | N/A |  |  |  | Jack Dioszeghy | 0% | Alex R | 0% |  | 0% | 0% | 2025-09-29 | 2025-11-10 |  | 2025-11-08 | 2025-12-15 | 5 |  | 2025-12-22 | 2025-12-31
Libby |  | 805476_DC_Senate SAA_IC22As0_02 |  | Matt | 805476 | 2025-12-30 |  | working |  | CDR - Superstructure-9/29/25 Delivery - 12/31/25 |  | Jack Dioszeghy | 0% | Finn S | 0% |  | 0% | 0% | 2025-08-04 | 2025-09-29 | N/A | 2025-12-01 | 2025-12-15 | 5 |  | 2025-12-22 | 2025-12-31
CFalls | RS / NM | 805337_DC_FEMA_MLOU_RK42As3_03 |  | Marie | 805337 | 2025-12-16 |  | N/A |  | Component Inspection - 11/7/25 Acceptance - 1/6/26 |  | Trevor Jobst | 0% | Finn S | 0% | Link G | 0% | 0% | 2025-07-14 | 2025-09-08 | 12/1-12/25 | 2025-12-14 | 2025-12-22 | 5 |  | 2025-12-29 | 2026-01-06 | ME Full CAD Complete
CFalls | NH / MF | 805568_GA_GTRI_Tacoma_02 |  | Shelden | 805568 | ASAP |  |  |  | Delivery - |  |  |  | Roger F |  |  |  |  | n/a | 2025-12-08 |  | n/a | 2025-12-22 | 5 |  | 2025-12-29
CFalls | JC / BH | 805308_MD_FEMA_MCOV_25 |  | Marie | 805308 | 2025-11-06 |  | Arrived |  | Superstructure - 11/3/25 Electrical - 11/21/25 Delivery - 1/9/26 | Done | Chance Morine | 100% | Martin J | 0% |  | 0% | 0% | 2025-09-22 | 2025-11-03 |  | N/A | 2025-12-29 | 5 |  | 2026-01-05 | 2026-01-09 | ME CAD Released, Executed 12/20
Libby |  | 805477_DC_Senate SAA_IC22As0_03 |  | Matt | 805477 | 2025-12-30 |  | working |  | CDR - Superstructure- Delivery - |  | Jack Dioszeghy | 0% | Finn S | 0% |  | 0% | 0% | 2025-09-15 | 2025-11-03 | N/A | 2025-12-15 | 2025-12-29 | 5 |  | 2026-01-05 | 2026-01-09
CFalls | DM / AL | 805351_AL_Shoals V.A._IC28As4_02 |  | Marie | 805351 | 2025-12-15 |  | working |  | Delivery - |  | Marcus Tokmak | 0% | Nick S | 0% | Link G | 0% | 0% | 2025-06-30 | 2025-08-25 |  | 2026-01-05 | 2026-01-12 | 5 |  | 2026-01-19 |  | Full CAD release commit 6/20/25
CFalls | DM / AL | 805472_MT_Custer County_D24 |  | Shelden | 805472 |  |  | N/A |  | PDR - 4/30/25 CDR - 9/17/25 Delivery - |  | Chaffin Ross | 0% | Nick S | 0% | Scott B | 0% | 0% | 2025-11-13 | 2025-12-01 |  | 2026-01-05 | 2026-01-12 | 5 |  | 2026-01-19 |  | Full ME CAD Commit 10/30/25
CFalls | RH / CO | 805582_FL_EglinAFB_CST-DRV_03 |  | Ashley | 805582 |  |  | N/A |  |  |  | Jack Dioszeghy | 0% | Alex R | 0% |  | 0% | 0% | 2025-10-27 | 2025-12-08 |  | 2026-01-05 | 2026-01-12 | 5 |  | 2026-01-19
CFalls | RH / CO | 805567_FL_EglinAFB_CST-DRV_04 |  | Ashley | 805567 |  |  | N/A | [5 empty] | Alex R | [5 empty] | 2025-12-08 |  | 2026-01-05 | 2026-01-12 | 5 |  | 2026-01-19
Libby |  | 805331_CA_Teledyne_C20 |  | Rick | 805331 | 2026-02-07 | DX | N/A |  | CDR - July 31 Superstructure - FAT - |  | Jeff Gaddy |  | Andrew B |  |  |  |  | 2025-09-02 | 2025-09-24 |  |  | 2025-12-01 | 42 |  | 2026-01-28 | 2026-02-02 | QC includes significant testing requirements with customer on site
CFalls | RS / NM | 805338_DC_FEMA_MLOU_RK42As3_04 |  | Marie | 805338 | 2026-01-30 |  | N/A |  | Component Inspection - 12/5/25 Acceptance -2/6/25 |  | Trevor Jobst | 0% | Finn S | 0% | Link G | 0% | 0% | 2025-08-18 | 2025-10-12 | 1/14-1/26 | 2026-01-19 | 2026-01-26 | 5 |  | 2026-02-02 |  | ME Full CAD Complete
CFalls | JC / BH | 805309_MD_FEMA_MCOV_26 |  | Marie | 805309 | 2025-11-06 |  | arrived w/issue |  | Superstructure - Electrical - Delivery - | Done | Chance Morine | 100% | Martin J | 100% |  | 100% | N/A | 2025-10-20 | 2025-12-01 |  | N/A | 2026-01-26 | 5 |  | 2026-02-02
CFalls | JN / NM | 805153_AL_Huntsville V.A._IC28As4_01 |  | Marie | 805153 | 2025-11-05 |  | working |  | Delivery - |  | Marcus Tokmak | 0% | Nick S | 0% | Link G | 0% | 0% | 2025-07-14 | 2025-09-08 |  | 2026-01-19 | 2026-01-26 | 5 |  | 2026-02-02 |  | Full CAD release 8/25/25
CFalls | NH / MF | 805296_MD_TribalCo_ICE_IC26As3 |  | Jason | 805296 | 2026-04-30 |  | June 2025 |  | PDR - 4/30/25 Delivery - 3/30/26 |  | Will Busching | 0% | William J | 0% |  | 0% | 0% | 2025-08-04 | 2025-09-29 |  | 2026-01-26 | 2026-02-01 | 5 |  | 2026-02-09 |  | Need SPEC red lines and updated sales drawing, Verbal approval for FEB contract date. We must ship as planned in Feb 2026 to manage international shipping time and delivery schedule. ME CAD Complete commit 7/30/25
Libby |  | 804487_AL_RedstoneTestCenter_RATH_R32As4 |  | Sam | 804487 | 2026-02-23 | DOA2 | N/A |  |  |  | Bryce Puchta | 0% | Andrew B | 0% |  | 0% | 0% | 2025-09-01 | 2025-10-06 |  | 2026-01-27 | 2026-02-09 | 10 |  | 2026-02-23 |  | Full CAD Release 9/7/25
Libby |  | 805359_NC_Wake County EM_IC32As4 |  | Matt | 805359 | 2026-02-26 |  | quoting |  | PDR - 5/1/25 CDR - Delivery - 2/27/26 |  | Ryan Van Marel | 0% | Finn S | 0% |  | 0% | 0% | 2025-09-29 | 2025-11-11 | N/A | 2026-02-11 | 2026-02-16 | 5 |  | 2026-02-23 |  | ME Full CAD commit 8/15/25
Libby |  | 805228_FL_96th Cybersecurity TS-64th TS_RK53As0 | GOOD | Jack | 805228 | 2026-05-08 |  |  |  | Design Acceptance - 10/11/1015 Delivery - 3/6/2026 |  | Trevor Jobst |  | Andrew B |  | Scott B |  |  | 2025-11-03 | 2025-12-08 |  |  |  | IN QC |  | 2026-02-27 | 2026-03-06 | 10/3/25 ME CAD Commit
CFalls | JC / BH | 805310_MD_FEMA_MCOV_27 |  | Marie | 805310 | 2025-11-06 |  | Mar 2025 |  | Superstructure - Electrical - Delivery - |  | Chance Morine | 100% | Martin J | 100% |  | 100% | N/A | 2025-11-17 | 2025-12-29 |  | N/A | 2026-02-23 | 5 |  | 2026-03-02 |  | ME CAD Released, Executed 12/20
CFalls | DM / AL | 804391_CA_SDPD_IC22As0 |  | Brian | 804391 |  |  | Arrived | [5 empty] | Finn S |  |  |  |  | 2025-11-24 | 2026-01-05 |  | 2026-02-16 | 2026-02-23 | 5 |  | 2026-03-02
CFalls | NH / MF | 805328_OH_Paralax Advanced Research_TCVMax |  | Brian | 805328 | 2026-04-03 |  |  |  | PDR - CDR - Dleivery - |  |  |  | Alex R |  |  |  |  | 2025-11-10 | 2025-12-22 |  | 2026-02-16 | 2026-02-13 | 11 |  | 2026-03-02
CFalls | JN / NM | 804505_ID_IdahoStatePolice_R32As3_01 |  | Marie | 804505 | 2026-05-21 |  | Arrived - need flatbed install |  | Delivery - 3/13/26 |  | Sean McGee | 0% | Parker R | 0% |  | 0% | 0% | 2025-10-06 | 2025-12-01 | Decals | 2026-02-23 | 2026-03-02 | 5 |  | 2026-03-09 |  | Does client have option to pay early if we deliver in 2025?, ME full CAD release commit 8/30/25
CFalls | DM / AL | 805186_AL_AuburnPublicSafety_IC28As2 |  | Jason | 805186 |  |  |  |  | PDR - 9/4/25 CDR - 10/23/25 Delivery 3/27-26 |  | Luke Zamoyski | 0% | Austin G | 0% |  | 0% | 0% | 2025-11-10 | 2026-01-05 |  | 2026-03-09 | 2026-03-16 | 5 |  | 2026-03-23 | 2026-03-27 | ME full CAD release commit 11/30/25
CFalls | RS / NM | 805339_DC_FEMA_MLOU_RK42As3_05 |  | Marie | 805339 | 2026-03-16 |  | N/A |  | Component Inspection - 2/2/26 Acceptance - 4/10/26 |  | Trevor Jobst | 0% | Finn S | 0% | Link G | 0% | 0% | 2025-10-20 | 2025-12-15 | 3/5-3/6/26 | 2026-03-23 | 2026-03-30 | 5 |  | 2026-04-06 |  | ME Full CAD Complete
CFalls | JC / BH | 805314_TX_Dynetics_IC14As0 |  | Shelden | 805314 | 2026-04-22 |  |  |  | PDR - CDR - Delivery - |  |  |  | Austin G |  |  |  |  | 2025-12-15 | 2026-01-26 |  | 2026-03-23 | 2026-03-30 | 5 |  | 2026-04-06
Libby |  | 805279_CA_JT4_IC14As0 FTS_01 | GOOD | Ashley | 805279 | NEED NEW | DOC9 | NEED NEW (KSU TAKING) | Gears | Monthly |  | Chaffin Ross | 0% | Roger F | 0% | Cody R | 0% | 0% | NEED NEW | NEED NEW | N/A | N/A | 2026-03-23 | 5 |  | 2026-04-06 |  | Risk: Eng on hold due to client deciding on floor layout mods. UPDATE: Moved to back of line per KSU/LV Additions
Libby |  | 805357_CA_JT4_IC14As0 FTS_02 | GOOD | Ashley | 805357 | NEED NEW | DOC9 | NEED NEW (LV TAKING) | Gears | Monthly |  | Chaffin Ross | 0% | Roger F | 0% | Cody R | 0% | 0% | NEED NEW | NEED NEW | N/A | N/A | 2026-03-30 | 5 |  | 2026-04-13 |  | Risk: Eng on hold due to client deciding on floor layout mods. UPDATE: Moved to back of line per KSU/LV Additions
Libby |  | 805292_CA_JT4_IC14As0 FTS_03 | GOOD | Ashley | 805292 | NEED NEW | DOC9 | Mar 2025 | Gears | Monthly |  | Chaffin Ross | 0% | Roger F | 0% | Cody R | 0% | 0% | NEED NEW | NEED NEW | N/A | N/A | 2026-04-06 | NO SHIP DATE |  | 2026-04-20 |  | Risk: Eng on hold due to client deciding on floor layout mods. UPDATE: Moved to back of line per KSU/LV Additions
CFalls | JN / NM | 805128_ID_IdahoStatePolice_R32As3_02 |  | Marie | 805128 | 2026-05-21 |  | Arrived - need flatbed install |  | Delivery - 4/30/26 |  | Luke Zamoyski | 0% | Parker R | 0% |  | 0% | 0% | 2025-11-24 | 2026-01-19 | Decals | 2026-04-13 | 2026-04-20 | 5 |  | 2026-04-27 |  | ME full CAD release 10/6/25
CFalls | NH / MF | 804924_OK_LawtonFD_IC34As4 |  | Jason | 804924 | 2026-06-21 |  |  |  | Already Paid in Full |  |  |  | Ethan S |  |  |  |  | 2025-12-15 | 2026-01-26 |  | 2026-04-20 | 2026-04-23 | 6 |  | 2026-05-02 | 2026-05-05
Libby |  | 805267_FL_VAMC_IC34As0_01 |  | Marie | 805267 | 2026-04-30 |  |  |  | Delivery - |  |  |  | Nick S |  |  |  |  | 2025-11-17 | 2025-12-29 |  | 2026-04-13 | 2026-04-20 | 10 |  | 2026-05-04
Libby |  | 805617_FL_VAMC_IC34As0_02 |  | Marie | 805617 | 2026-04-30 |  |  |  | Delivery - |  |  |  | Nick S |  |  |  |  | 2025-11-17 | 2025-12-29 |  | 2026-04-13 | 2026-04-20 | 10 |  | 2026-05-04
CFalls | RS / NM | 805340_DC_FEMA_MLOU_RK42As3_06 |  | Marie | 805340 | 2026-04-30 |  | N/A |  | Component Inspection - 3/9/26 Acceptance - 5/15/26 |  | Trevor Jobst | 0% | Finn S | 0% | Link G | 0% | 0% | 2025-11-24 | 2026-01-18 | 4/13-4/14/26 | 2026-04-27 | 2026-05-04 | 5 |  | 2026-05-11 |  | ME Full CAD Complete
Libby |  | 803944_AL_RTC_ACDC Trailer |  | Mike P | 803944 | 2026-10-05 | [12 empty] | 2026-01-12 | 2026-03-09 |  | 2026-08-10 | 2026-08-24 | 10 |  | 2026-09-07
Libby |  | 805387_OK_Verizon_Upfit |  | Shelden | 805387 | 2025-03-30 |  | N/A | N/A | Paid in Full | Done | Will Busching | 100% | Roger F | 100% |  | 0% | N/A | N/A | in work | Logos | N/A | TBD | NO SHIP DATE | TBD | TBD | TBD | Bumper damaged needing redone
CFalls | NH / MF | 803932_SC_DSIT_TCT-HD | MINOR ISSUE | Shelden | 803932 | 2025-11-27 |  | n/a |  | CDR - 3/21/25 Completion - 7/21/25 Delivery - 7/25/25 |  | John Phillips | 100% | Calvin C | 100% |  | 100% | 100% | N/A | in work |  | TBD | TBD | NO SHIP DATE |  | TBD | TBD | Tongue rework full CAD release commit 5/2/25. Need to undstand work content.
Libby |  | 805109_MT_NomadGCS_Conex_TM03PROTO |  |  | 805109 | [8 empty] | Roger F | [5 empty] | paused | N/A | 2024-11-11 | 2024-12-16 | NO SHIP DATE |  | TBD | TBD
CFalls | FSW | 803533_NY_DHSES RAMER_TCT-C_01_Frame Repair |  |  | 803533 | [18 empty] | NO SHIP DATE |  |  | 2025-05-30
CFalls | FSW | 804614_NY_DHSES RAMER_TCT-C_02_Frame Repair |  |  | 804614 | [18 empty] | NO SHIP DATE |  |  | 2025-05-30
Field | FSW | 803955_FL_ColeEngineeringServices_D16_01 |  |  | 803955 | 2025-02-07 | [8 empty] | 5% |  |  |  |  | IF? |  |  |  | NO SHIP DATE |  |  | 2025-05-19 | Need these kitted and shipped by May 10th
Field | FSW | 803956_FL_ColeEngineeringServices_D16_02 |  |  | 803956 | 2025-02-07 | [13 empty] | IF? |  |  |  | NO SHIP DATE |  |  | 2025-05-19 | Need these kitted and shipped by May 10th
Field | FSW | 804192_FL_ColeEngineeringServices_D16_03 |  |  | 804192 | 2025-02-21 | [13 empty] | IF? |  |  |  | NO SHIP DATE |  |  | 2025-05-19 | Need these kitted and shipped by May 10th
Field | FSW | 804193_FL_ColeEngineeringServices_D16_04 |  |  | 804193 | 2025-02-21 | [13 empty] | IF? |  |  |  | NO SHIP DATE |  |  | 2025-05-19 | Need these kitted and shipped by May 10th
Field | FSW | 804194_FL_ColeEngineeringServices_D16_05 |  |  | 804194 | 2025-03-07 | [13 empty] | IF? |  |  |  | NO SHIP DATE |  |  | 2025-05-19 | Need these kitted and shipped by May 10th
Field | FSW | 804195_FL_ColeEngineeringServices_D16_06 |  |  | 804195 | 2025-03-07 | [13 empty] | IF? |  |  |  | NO SHIP DATE |  |  | 2025-05-19 | Need these kitted and shipped by May 10th
Field | FSW | 802582-01_MT_RedLodgeFireDepartment_TCV Upfit | MINOR ISSUE |  | 802582-01 | [18 empty] | NO SHIP DATE |  |  | 2025-05-30 | ISSUE: Electrical concerns.
Field | FSW | 803569_NY_DHSES_ROW2_ Parts Kit |  |  | 803569 | 2025-04-01 | [17 empty] | NO SHIP DATE |  |  | 2025-04-26 | SHIPPED
Field | FSW | 803570_NY_DHSES_ROW3_Parts Kit |  |  | 803570 | 2025-04-01 | [17 empty] | NO SHIP DATE |  |  | 2025-04-26 | SHIPPED
Field | FSW | 803571_NY_DHSES_ROW4_Parts Kit |  |  | 803571 | 2025-04-01 | [17 empty] | NO SHIP DATE |  |  | 2025-04-26 | SHIPPED
Field | FSW | 803572_NY_DHSES_ROW5_Parts Kit |  |  | 803572 | 2025-04-01 | [17 empty] | NO SHIP DATE |  |  | 2025-04-26 | SHIPPED
Field | FSW | 803574_NY_DHSES_ROW7_Parts Kit |  |  | 803574 | 2025-04-01 | [17 empty] | NO SHIP DATE |  |  | 2025-04-26 | SHIPPED
Field | FSW | 803575_NY_DHSES_ROW8_Parts Kit |  |  | 803575 | 2025-04-01 | [17 empty] | NO SHIP DATE |  |  | 2025-04-26 | SHIPPED
CFalls |  | 805271_MT_Nomad_ManPortableKit_Prototype |  |  | 805271 | [8 empty] | Brett B | 100% | [8 empty] | NO SHIP DATE
Field | FSW | 804844_NY_BinghamtonPD_IT Refresh |  |  | 804844 | 2025-11-30 | [17 empty] | NO SHIP DATE |  |  | 2025-09-30
Field | FSW | 802960_GA_Zodiac_D16ANT02 |  |  | 802960 | [18 empty] | NO SHIP DATE |  |  | 2025-05-30 | SHIPPED
Field | FSW | 803507_GA_ZDS_D16ANT_1 |  |  | 803507 | [18 empty] | NO SHIP DATE |  |  | 2025-05-30 | SHIPPED
Field | FSW | 803544_GA_ZDS_D16ANT_2 |  |  | 803544 | [18 empty] | NO SHIP DATE |  |  | 2025-05-30 | SHIPPED
Field | FSW | 803545_GA_ZDS_D16ANT_3 |  |  | 803545 | [18 empty] | NO SHIP DATE |  |  | 2025-05-30 | SHIPPED
Field | FSW | 803546_GA_ZDS_D16ANT_4 |  |  | 803546 | [18 empty] | NO SHIP DATE |  |  | 2025-05-30 | SHIPPED
Field | FSW | 804205_NV_LVMPD_IC14As0 | MINOR ISSUE |  | 804205 | [18 empty] | NO SHIP DATE |  |  | 2025-05-30 | One final part from FAB to ship assembly to truck.
|  | 805528_OK_VerizonMERIT_F350_01 |  | Shelden | 805528 | 2025-12-31 |  |  |  | PDR - CDR - Delivery - | [13 empty] | NO SHIP DATE
|  | 805648_OK_VerizonMERIT_F350_02 |  | Shelden | 805648 | 2025-12-31 |  |  |  | PDR - CDR - Delivery - | [13 empty] | NO SHIP DATE
|  | 805529_OK_VerizonMERIT_F550 |  | Shelden | 805529 | 2025-12-31 |  |  |  | PDR - CDR - Delivery - | [13 empty] | NO SHIP DATE
|  | 805626_AL_TCS Antenna System Purchase_EMSA Task |  |  | 805626 | [18 empty] | NO SHIP DATE
Note on C14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Neverdown
Note on U19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Fab ETIC 2/6
Note on C22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Neverdown
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Neverdown
Note on C27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Neverdown
Note on C46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Neverdown
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Neverdown
Note on C49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Neverdown
Note on C61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Neverdown
Note on C87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Neverdown