## Master
Project Name | Original Contract Date | # of Formal Extensions (Final Contract Date) | Actual Delivery Date | # of days pre/post contract | Category | Late due to: Client Nomad Vendor | Late Reasoning
803991_NM_RobertsTruckBernalilloCo_IC26As0_02 | 2023-04-12 |  | 2024-09-13 | -520 | Over 90 DAYS LATE | Client | Late CSE Chassis Arrival
803990_NM_RobertsTruckBernalilloCo_IC26As0_01 | 2023-04-12 |  | 2024-07-30 | -475 | Over 90 DAYS LATE | Client | Late CSE Chassis Arrival
804289_MT_LoganHealth_IC24As1_02 | 2023-07-29 |  | 2024-05-13 | -289 | Over 90 DAYS LATE | Vendor | Late Chassis Arrival
803789_MT_LoganHealth_IC24As1_01 | 2023-07-29 |  | 2024-01-26 | -181 | Over 90 DAYS LATE | Vendor | Late Chassis Arrival
804190_GA_Coweta Co_IC34As4 | 2023-09-12 |  | 2024-03-22 | -192 | Over 90 DAYS LATE | Nomad | Sales sold an unavailable chassis with no availability in sight. Customer was adamant about the original chassis - we jumped through many hoops trying to find something that would meet spec and they would agree upon which proved difficult based on their strongly desired requirement.
804325_VA_ADS_WSMR_MOSS_IC20As1_02 | 2023-09-26 | x3 (2/2/24) | 2024-03-01 | -157 | Over 90 DAYS LATE | Vendor | Late arrival of HVACs
804092_VA_ADS_WSMR_MOSS_IC20As1_01 | 2023-09-26 | x3 (2/2/24) | 2024-02-08 | -135 | Over 90 DAYS LATE | Vendor | Late arrival of HVACs
800024-01_NH_Grafton Co_Upgrades | 2023-12-14 |  | 2024-03-07 | -84 | 40 to 89 Days Late | Nomad | Vague requirments during sales resulted in additional definition for build
804376_MD_VA_Mobile Medical_IC20As0_06 | 2023-12-18 |  | 2024-01-20 | -33 | Less than 40 Days Late | Vendor | Late Chassis Arrival
803426-01_CA_EdwardsAFB_IC26Reconfig | 2023-12-19 |  | 2024-06-26 | -190 | Over 90 DAYS LATE | Nomad | Engineering delays
804377_MD_VA_Mobile Medical_IC20As0_07 | 2023-12-22 |  | 2024-02-28 | -68 | 40 to 89 Days Late | Vendor | Late Chassis Arrival
804589_MT_NomadGCS_TCV Max Demo | 2023-12-31 |  | 2024-03-18 | -78 | 40 to 89 Days Late | Vendor | Late arrival of HVACs
804378_MD_VA_Mobile Medical_IC20As0_08 | 2024-01-22 |  | 2024-03-08 | -46 | 40 to 89 Days Late | Vendor | Late Chassis Arrival
804379_MD_VA_Mobile Medical_IC20As0_09 | 2024-01-29 |  | 2024-04-10 | -72 | 40 to 89 Days Late | Vendor | Late Chassis Arrival
804205_NV_LVMPD_IC14As0 | 2024-01-31 |  | 2024-02-08 | -8 | Less than 40 Days Late | Vendor | Late Chassis Arrival
804237_GA_EPA_IC14As2 | 2024-02-11 |  | 2024-03-27 | -45 | 40 to 89 Days Late | Vendor | Late Chassis Arrival
804166_MT_LewisClarkSheriffsOffice_IC34As4 | 2024-02-15 |  | 2024-05-21 | -96 | Over 90 DAYS LATE | Vendor | Late Chassis Arrival
804638_ID_MoPoc_Van_13 | 2024-02-19 |  | 2024-02-08 | 11 | On time | On Time
804636_ID_MoPoc_Van_11 | 2024-02-19 |  | 2024-02-08 | 11 | On time | On Time
804637_ID_MoPoc_Van_12 | 2024-02-19 |  | 2024-02-08 | 11 | On time | On Time
804634_ID_MoPoc_Van_09 | 2024-02-19 |  | 2024-02-02 | 17 | On time | On Time
804635_ID_MoPoc_Van_10 | 2024-02-19 |  | 2024-02-02 | 17 | On time | On Time
804380_MD_VA_Mobile Medical_IC20As0_10 | 2024-02-26 |  | 2024-04-17 | -51 | 40 to 89 Days Late | Nomad | Failed to order AVL on time
804333_DC_EPA_MAM_Sprinter_01 | 2024-02-29 | x1 (6/28/24) | 2024-08-30 | -183 | Over 90 DAYS LATE | Vendor | Third Party Equipment Install
804848_DC_EPA_MAM_Sprinter_03 | 2024-02-29 | x1 (6/28/24) | 2024-08-30 | -183 | Over 90 DAYS LATE | Vendor | Third Party Equipment Install
804847_DC_EPA_MAM_Sprinter_02 | 2024-02-29 | x1 (6/28/24) | 2024-08-02 | -155 | Over 90 DAYS LATE | Vendor | Third Party Equipment Install
804228_MA_MAFireServices_D24As2 | 2024-03-08 | x1 (4/26/24) | 2024-06-03 | -87 | 40 to 89 Days Late | Nomad | Engineering design issues
804388_MD_FEMA_MCOV_13 | 2024-03-20 | x2 (9/30/24) | 2024-09-30 | -194 | Over 90 DAYS LATE | Vendor | Chassis arrival late & vibration/wheel issues
804404_MD_FEMA_MCOV_14 | 2024-03-20 | x1 (6/15/24) | 2024-08-13 | -146 | Over 90 DAYS LATE | Vendor | Chassis arrival late & vibration/wheel issues
804178_OK_ONEOK_TCVMAX_01 | 2024-04-01 |  | 2024-06-14 | -74 | 40 to 89 Days Late | Client | Client Mod
804501_OK_ONEOK_TCVMAX_02 | 2024-04-01 |  | 2024-06-14 | -74 | 40 to 89 Days Late | Client | Client Mod
803749_MT_FlatheadCounty_IC28As2 | 2025-01-22 |  | 2024-06-19 | 217 | On time | On Time
803851-01_NJ_Verizon_TCTHD_Upgrades | 2024-04-13 |  | 2024-02-01 | 72 | On time | On Time
804283_VA_ADS_GuamSecurity_TCT | 2024-04-29 |  | 2024-03-19 | 41 | On time | On Time
804692_FL_PascoCSO_SOV_01 | 2024-06-30 |  | 2024-06-26 | 4 | On time | On Time
804693_FL_PascoCSO_SOV_02 | 2024-06-30 |  | 2024-06-26 | 4 | On time | On Time
804300_CA_YubaCountyProbation_IC26As0 | 2024-07-25 |  | 2024-05-23 | 63 | On time | On Time
804786_WV_FBI_MobileForensicLab_Sprinter_06 | 2024-08-29 |  | 2024-08-29 | 0 | On time | On Time
804784_WV_FBI MFL_Sprinter_04 | 2024-08-29 |  | 2024-07-26 | 34 | On time | On Time
804785_WV_FBI MFL_Sprinter_05 | 2024-08-29 |  | 2024-07-26 | 34 | On time | On Time
804433_TX_Rohde&Schwarz_SOV | 2024-09-01 |  | 2024-08-30 | 2 | On time | On Time
803932_SC_DSIT_TCT-HD | 2024-09-24 |  | 2024-09-22 | 2 | On time | On Time
804823_DC_ATF_Sprinter_02 | 2024-09-27 |  | 2024-09-06 | 21 | On time | On Time
803946_SC_HorryCountyPD_IC18As0 | 2024-10-22 |  | 2024-09-04 | 48 | On time | Vendor | Chassis arrival late & vibration/wheel issues
804703_DC_ATF_Sprinter_01 | 2024-09-27 |  | 2024-08-27 | 31 | On time | On Time
804824_DC_ATF_Sprinter_03 | 2024-09-27 |  | 2024-10-02 | -5 | Less than 40 Days Late | Nomad | Nomad electrical error with van lights. Had to send to Spokane for reprogramming
804565_MD_FEMA_MCOV_15 | 2024-09-29 | x1 (12/31/24) | 2024-10-04 | -5 | Less than 40 Days Late | Vendor | Chassis arrival late & vibration/wheel issues
804570_MD_FEMA_MCOV_16 | 2024-09-29 | x1 (12/31/2024) | 2024-10-22 | -23 | Less than 40 Days Late | Vendor | Chassis arrival late & vibration/wheel issues
804106_AL_ADS_USACE_IC34As4_01 | 2025-01-17 |  | 2024-10-22 | 87 | On time | On Time
804826_DC_ATF_Sprinter_05 | 2024-09-27 | x1 (12/29/2024) | 2024-10-23 | -26 | Less than 40 Days Late | Client | Client Mod
804825_DC_ATF_Sprinter_04 | 2024-09-27 | x1 (12/29/2024) | 2024-10-23 | -26 | Less than 40 Days Late | Client | Client Mod
804486_TX_TMobile_D22_SatCOW_01 | 2024-02-06 |  | 2024-10-25 | -262 | Over 90 DAYS LATE | Nomad | Under bid project duration (365 ARO)
804571_MD_FEMA_MCOV_17 | 2024-09-29 | x1 (12/31/24) | 2024-11-15 | -47 | 40 to 89 Days Late | Vendor | Chassis arrival late & vibration/wheel issues
804905_ID_MoPOC_Van_17 | 2024-11-23 |  | 2024-11-22 | 1 | On time | On Time
803750_TX_TMobile_SatCOLT_01 | 2024-02-13 |  | 2024-12-03 | -294 | Over 90 DAYS LATE | Nomad | Under bid project duration (365 ARO)
803533_NY_DHSES RAMER_TCT-C_01 | 2024-10-01 | x1 (10/25/2024) | 2024-12-04 | -64 | 40 to 89 Days Late | Nomad | Impacted by Colts / wrong roof type spec'd in sales
804614_NY_DHSES RAMER_TCT-C_02 | 2024-10-01 | x1 (10/25/2024) | 2024-12-04 | -64 | 40 to 89 Days Late | Nomad | Impacted by Colts / wrong roof type spec'd in sales
804904_ID_MoPOC_Van_16 | 2024-11-25 |  | 2024-12-05 | -10 | Less than 40 Days Late | Nomad | Powered step retrofit. We did not purchase the correct step, then couldn't find a good alternative and ended up retrofitting the OEM step.
804903_ID_MoPOC_Van_15 | 2024-12-12 |  | 2024-12-13 | -1 | Less than 40 Days Late | Nomad | Powered step retrofit. We did not purchase the correct step, then couldn't find a good alternative and ended up retrofitting the OEM step.
804664_ID_MoPOC_Van_14 | 2024-12-12 |  | 2024-12-11 | 1 | On time | On Time
804906_ID_MoPOC_Van_18 | 2024-12-29 |  | 2024-12-20 | 9 | On time | On Time
800812_DC_DCWater_CCTV_1 | 2025-01-31 |  | 2025-01-03 | 28 | On time | On Time
803913_AL_GAN-REDSTONE_ECTM_01 | 2025-01-25 |  | 2025-01-08 | 17 | On time | On Time
804469_INT_USAF_48MXG_R30 | 2025-09-25 |  | 2025-01-21 | 247 | On time | On Time
804082_DC_DepartmentOfState_Moldova_IC20As0 | 2024-02-16 | x4 (1/31/25) | 2025-01-15 | -334 | Over 90 DAYS LATE | Vendor | Late Chassis Arrival
804572_MD_FEMA_MCOV_18 | 2024-09-29 | x2 (2/28/25) | 2025-01-17 | -110 | Over 90 DAYS LATE | Vendor | Vibration/wheel issue
804538_AL_GaN_MOSAIC_Backend_01 | 2024-09-13 |  | 2025-01-17 | -126 | Over 90 DAYS LATE | Nomad | Production Delays
804539_AL_GaN_MOSAIC_Backend_02 | 2024-10-18 |  | 2025-01-17 | -91 | Over 90 DAYS LATE | Nomad | Production Delays
804485_TX_TMobile_SatCOLT_03 | 2024-02-13 |  | 2025-01-21 | -343 | Over 90 DAYS LATE | Nomad | Under bid project duration (365 ARO)
804198_AL_RedstoneTestCenter_TCV-MAX | 2025-01-24 |  | 2025-01-22 | 2 | On time | On Time
804215_OK_VerizonMERIT_IC20As0 | 2025-03-15 |  | 2025-02-05 | 38 | On time | On Time
804936_VA_BlueHalo_PHEL_MobileSupport | 2025-03-21 |  | 2025-03-03 | 18 | On Time | On Time
804088_VA_BlueHalo_PHEL_CleanRoom | 2025-03-21 |  | 2025-03-03 | 18 | On Time | On Time
804543_AL_GaN_MOSAIC_Power | 2024-09-17 |  | 2025-03-17 | -181 | Over 90 DAYS LATE | Nomad | Production Delays
804186_AL_GaN_MOSAIC_C2 | 2024-09-17 |  | 2025-03-17 | -181 | Over 90 DAYS LATE | Nomad | Production Delays
804830_TX_GDIT_Raven3_Defender | 2025-04-29 |  | 2025-03-25 | 35 | On Time | On Time
804510_TX_GDIT_TCVMAX | 2025-04-29 |  | 2025-03-25 | 35 | On Time | On Time
804452_FL_SeminoleTribe_TCV-Max | 2025-09-20 |  | 2025-03-28 | 176 | On Time | On Time
804573_MD_FEMA_MCOV_19 | 2024-09-29 | x2 (2/28/25) | 2025-04-17 | -200 | Over 90 DAYS LATE | Vendor | vibration/wheel issue
803863_CA_EdwardsAFB_D20 | 2024-08-30 | x5 (4/30/2025) | 2025-04-18 | -231 | Over 90 DAYS LATE | Nomad | Production Delays
804810_MD_VA_MVCs_Sprinter_02 | 2025-03-25 |  | 2025-04-24 | -30 | Less than 40 Days Late | Nomad | Production Delays
804811_MD_VA_MVCs_Sprinter_03 | 2025-03-25 |  | 2025-04-24 | -30 | Less than 40 Days Late | Nomad | Production Delays
804812_MD_VA_MVCs_Sprinter_04 | 2025-03-25 |  | 2025-04-24 | -30 | Less than 40 Days Late | Nomad | Production Delays
804708_MD_VA_MVCs_Sprinter_01 | 2025-03-25 |  | 2025-04-24 | -30 | Less than 40 Days Late | Nomad | Production Delays
804652_AL_ADS_USACE_IC34As4_02 | 2025-01-17 |  | 2025-04-30 | -103 | Over 90 DAYS LATE | Nomad | Production Delays, issue in route
804887_CA_CityOfMonterey_Sprinter | 2025-05-23 |  | 2025-04-29 | 24 | On Time | On Time
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0