## Template
Project Number | Milestone | Amount | Target Invoice Date | Actual Invoice Date | Payment Received Date | Status | Description | Contract Reference | Payment Terms | Invoice Number | Percentage of Total | Billing Contact | Notes
805472 | MS #2 - 30% PDR | 69600 | 2025-05-08
804813 | MS #1 - 100% Delivery | 131908 | 2025-05-13
805067 | MS #2 - 10% PDR | 147641 | 2025-05-14
804814 | MS #1 - 100% Delivery | 145389 | 2025-05-15
804507 | MS #3 - 25% Delivery | 372857 | 2025-05-15
804656 | MS #3 - Electrical Rough-In | 433657 | 2025-05-16 | [9 empty] | Team is occupied by other units first
804666 | MS #1 - 100% Delivery | 698425 | 2025-05-16
804653 | MS #4 - 20% Delivery | 289105 | 2025-05-19
804816 | MS #1 - 100% Delivery | 152129 | 2025-05-22
804731 | MS #1 - 100% Delivery | 1251680 | 2025-05-23 | [9 empty] | Ceramic coating needed in route to delivery
804287 | MS #4 - 10% Delivery | 420683 | 2025-05-26 | [9 empty] | Engineering revisions & IT Integration. Really scheduled 5/29
804916 | MS #3 - 25% Delivery | 93726 | 2025-05-30 | [9 empty] | Needs to get wrapped internally
804654 | MS #4 - 20% Delivery | 289105 | 2025-06-16 | [9 empty] | e-chain lead time 3-4 weeks.
804815 | MS #1 - 100% Delivery | 188077 | 2025-05-28
804907 | MS #1 - 100% Delivery | 507470 | 2025-05-30 | [9 empty] | Tyler working with Brandon to see how we can hit that date
804484 | MS #3 - 34% Delivery | 385133 | 2025-06-03 | [9 empty] | AVL ESD 5/15/25
804018 | MS #3 - 34% Delivery | 894746 | 2025-06-06 | TBD | [8 empty] | Could be done early - look into how funding is structured. Connect with Daniel on this.
804273 | MS #5 - Electrical Rough-In | 89716 | 2025-06-13 | [9 empty] | EMI door arrival early May driving a late start in assembly.
804503 | MS #4 - Delivery | 490041 | 2025-06-13 | [9 empty] | HVAC Controller just ordered - 4 week delivery plus R&D effort
804545 | MS #4 - 10% Delivery | 75234 | 2025-06-20
805206 | MS #4 - 10% Delivery | 75234 | 2025-06-20
804862 | MS #4 - 10% Delivery | 29030 | 2025-06-20
806503 | EU-1 Delivery | 18104 | 2025-07-05 | [9 empty] | Aligned Date with monthly invoice date. Delivery is on track
804542 | Delivery | 120786 | 2025-06-24 | 2025-07-10 | [8 empty] | Delays are expected due to the nature of the prototype work
800582 | MS #3 - 20% AV and Comm Delivery | 52354 | 2025-06-25
800582 | MS #4 - 10% Delivery | 26177 | 2025-06-25
805214 | MS #4 - 10% Delivery | 29030 | 2025-06-27
804655 | MS #4 - 20% Delivery | 289105 | 2025-06-27
805040 | MS #4 - 10% Delivery | 52503 | 2025-07-03
804450 | MS #5 - 5% Delivery of Final Docs | 17838 | 2025-07-08
805304 | MS #4 - 10% Delivery | 56058 | 2025-07-11
804817 | MOD - Doors | 3402 | 2025-07-11 | [9 empty] | Working on Sprinters first.
804817 | MS #1 - 100% Delivery | 263625 | 2025-07-11 | [9 empty] | Working on Sprinters first.
804818 | MS #1 - 100% Delivery | 347368 | 2025-07-11 | [9 empty] | Working on Sprinters first.
804819 | MS #1 - 100% Delivery | 365977 | 2025-07-11 | [9 empty] | Working on Sprinters first.
804820 | MS #1 - 100% Delivery | 370630 | 2025-07-11 | [9 empty] | Working on Sprinters first.
804821 | MS #1 - 100% Delivery | 384587 | 2025-07-11 | [9 empty] | Working on Sprinters first.
804822 | MS #1 - 100% Delivery | 389239 | 2025-07-11 | [9 empty] | Working on Sprinters first.
804273 | MS #6 - Mast | 50625 | 2025-07-31
806504 | EU-2 Delivery | 18104 | 2025-08-11 | 2025-09-05 | [8 empty] | Aligned Date with monthly invoice date. Delivery is on track
805207 | MS #4 - 10% Delivery | 75234 | 2025-08-22
805203 | MS #4 - 10% Delivery | 29031 | 2025-08-22
804540 | Delivery | 120786 | 2025-08-29 | 2025-09-15 | [8 empty] | Need to complete FSS First
804541 | Delivery | 120786 | 2025-08-29 | 2025-09-15 | [8 empty] | Need to complete FSS First
804772 | MS #1 - 100% Delivery | 1912082 | 2025-09-05
804874 | MS #3 - 25% Delivery | 100727 | 2025-09-09
804893 | MS #1 - 100% Delivery | 915883 | 2025-09-08 | 2025-09-26
804273 | Event 7 - Final EMI Test | 50625 | 2025-09-26
804656 | MS #4 - 20% Delivery | 289105 | 2025-09-26
805228 | MS #1 - 100% Project Acceptance | 199500 | 2025-09-30
804273 | MS #8 - Delivery | 175000 | 2025-10-17 | [9 empty] | EMI Doors arriving beginning of May. Holds up Fabrication and EMi testing prior to assembly.
805306 | MS #4 - 10% Delivery | 29031 | 2025-10-17
805198 | MS #1 - 100% Delivery | 987943 | 2025-10-24
805120 | MS #4 - 10% Delivery | 66076 | 2025-11-07
804886 | MS #3 - 25% Delivery | 247224 | 2025-11-21
805326 | MS #2 - 50% Delivery | 188070 | 2025-11-28
804264 | MS #4 - 10% Delivery | 38641 | 2025-11-29
805307 | MS #4 - 10% Delivery | 29031 | 2025-12-12
803267 | MS #4 - 10% Delivery | 122837 | 2025-12-31
804684 | MS #4 - 10% Delivery | 181800 | 2025-12-31
805049 | Monthly Progress #9 | 81714 | 2025-05-01 | 2025-05-01 | [8 empty] | Billed.
805132 | Monthly Progress #9 | 268258 | 2025-05-12 | 2025-05-01 | [8 empty] | Billed.
805296 | MS #3 - PDR | 220940 | 2025-04-30 | 2025-05-06 | [8 empty] | Billed.
804881 | MS #3 - 30% CDR | 326044 | 2025-06-27 | 2025-06-09 | [8 empty] | Customer availability caused delay
804884 | MS #4 - 10% Delivery | 52900 | 2025-05-13
805201 | Monthly Progress #9 | 169593 | 2025-05-13
805197 | MS #9 - Monthly Progress #5 | 33500 | 2025-05-16
805207 | MS #3 - 20% Superstructure | 150468 | 2025-05-30 | [9 empty] | Fab in work. May pull in
805049 | Monthly Progress #10 | 81714 | 2025-06-01
805120 | MS #3 - 30% CDR | 198229 | 2025-06-02
806503 | EU-1 Test Complete | 18104 | 2025-06-05 | [9 empty] | Aligned Date with monthly invoice date. Asking Kratos if we can bill "test complete" outside of monthly to keep invoice in June.
806504 | EU-2 Assembly Complete | 72414 | 2025-06-05 | [9 empty] | Aligned Date with monthly invoice date. Delivery is on track
806503 | EU-1 Assembly Complete | 72414 | 2025-06-05 | [9 empty] | Completion date: 5/23. Invoice date will be 6/5
804874 | MS #2 - 25% Superstructure | 100727 | 2025-06-09
805132 | Monthly Progress #10 | 268258 | 2025-06-11
805201 | Monthly Progress #10 | 169593 | 2025-06-13
805197 | MS #6 - Monthly Progress | 33500 | 2025-06-16
804450 | MS #4 - 10% Acceptance at Factory | 35675 | 2025-06-16
805203 | MS #2 - 20% Superstructure | 58059 | 2025-06-16
804264 | MS #2 - 20% CAD Completion | 115200 | 2025-06-18
804347 | MS #3 - 30% Exposed Components Inspection | 248072 | 2025-06-26
805157 | MS #2 - 30% CDR | 678413 | 2025-06-30
805049 | Monthly Progress #11 | 81714 | 2025-07-01
806504 | EU-2 Test Complete | 18104 | 2025-07-05 | [9 empty] | Aligned Date with monthly invoice date. Delivery is on track
805203 | MS #3 - 20% Electrical Rough-in | 58059 | 2025-07-07
805132 | Monthly Progress #11 | 268258 | 2025-07-11
805201 | Monthly Progress #11 | 169593 | 2025-07-14
805347 | MS #4 - Battery Systems | 187291 | 2025-07-14
805197 | MS #7 - Monthly Progress | 33500 | 2025-07-16
805359 | MS #3 - 30% CDR | 262459 | 2025-07-16
805067 | MS #3 - 10% CDR | 147641 | 2025-07-30
805331 | MS #2 - 30% CDR | 259784 | 2025-07-31 | [9 empty] | Moved up based on customer request
805049 | Monthly Progress #12 | 81714 | 2025-08-01
805306 | MS #2 - 20% SuperStructure | 58059 | 2025-08-11
805201 | Monthly Progress #12 | 169593 | 2025-08-13
805197 | MS #10 - Monthly Progress #6 | 33500 | 2025-08-18
804347 | MS #3 - 30% Component Inspection | 248072 | 2025-08-21
805306 | MS #3 - 20% Electrical Rough-In | 58059 | 2025-08-29
805067 | Monthly Progress #5 - Chassis Arrival | 147641 | 2025-08-30
805049 | Monthly Progresss #13 | 56677 | 2025-09-01
805308 | MS #2 - 20% Superstructure | 58059 | 2025-09-01
805328 | MS #2 - 30% PDR | 271168 | 2025-09-03
805132 | Monthly Progresss #12 | 76500 | 2025-09-09
805308 | MS #3 - 20% Electrical Rough-in | 58059 | 2025-09-15
805309 | MS #2 - 20% Superstructure | 58059 | 2025-09-15
805347 | MS #5 - Roof Complete | 187291 | 2025-09-15
804264 | MS #3 - 10% Superstructure | 57600 | 2025-09-16
805472 | MS #3 - 30% CDR | 69600 | 2025-09-17
804391 | MS #2 - 25% CDR | 143700 | 2025-09-17
804347 | MS #4 - 20% Acceptance | 240575 | 2025-09-17
805197 | MS #11 - Monthly Progress #7 | 67000 | 2025-09-25
805337 | MS #3 - 30% Exposed Components Inspection | 248072 | 2025-09-25
805309 | MS #3 - 20% Electrical Rough-In | 58059 | 2025-09-29
805476 | MS #3 - 30% Superstructure | 231416 | 2025-09-29
805067 | Monthly Progress #5 - Chassis Arrival | 147641 | 2025-09-30
805049 | Monthly Progresss #14 | 28338 | 2025-10-01
805306 | MS #2 - 20% Superstructure | 58059 | 2025-10-06
804613 | MS #2 - 40% Shelter Frame | 247543 | 2025-10-10
805477 | MS #3 - 30% SuperStructure | 215582 | 2025-10-13
805157 | MS #3 - 30% SuperStructure | 231416 | 2025-10-20
805306 | MS #3 - 20% Electrical Rough-In | 58059 | 2025-10-24
805359 | MS #2 - 30% PDR | 262459 | 2025-04-30 | 2025-05-01 | [8 empty] | Billed.
804928 | MS #1 - 100% Delivery | 872263 | 2025-07-04 | TBD | [8 empty] | Potential pull-in to May.
804621 | MS #2 - 70% Delivery | 527683 | 2025-06-30 | [9 empty] | Came back and Nomad damaged it and needs graphics
805184 | MS #4 - 10% Delivery | 60806 | 2025-09-12
805319 | MS #4 - 10% Delivery | 60996 | 2025-09-25
805143 | MS #2 - 50% Delivery | 62961 | 2025-12-31 | [9 empty] | Adjusted to forecast
805296 | MS #4 - Delivery | 140470 | 2026-03-31 | [9 empty] | can't enter this date because it isn't open.
805626 | Material | 553532 | 2025-05-01 | 2025-05-01 | [8 empty] | Billed.
804273 | MOD - CDR | 86923 | 2025-05-30 | 2025-05-05 | [8 empty] | Billed.
803950-02 | MS #1 - 100% Completion | 6400 | 2025-07-31 | 2025-05-05 | [8 empty] | Billed.
805079 | MS #1 - 30% PO | 413479 | 2025-05-09
803944 | MS #9 - Traceability Matrix | 207850 | 2025-05-30
803944 | MS #10 - Integrated Master Schedule | 207850 | 2025-05-30
805314 | MS #2 - 25% PDR | 147662 | 2025-07-15
805528 | Chassis Delivery | 180080 | 2025-07-16
805529 | Chassis Delivery | 92478 | 2025-07-16
805314 | MS #3 - 25% CDR | 147662 | 2025-09-23
805347 |  | 187291 | 2025-10-14
805079 | MS #2 - 30% Chassis Order | 413479 | 2025-10-15
805347 |  | 468227 | 2025-10-22
805338 | MS #3 - 30% Exposed Components Inspection | 248072 | 2025-10-23
805308 | MS #4 - 10% Delivery | 29031 | 2025-10-27
805347 |  | 468227 | 2025-10-29
805067 | Monthly Progress #6 | 73821 | 2025-10-30
805186 | MS #2 - 20% PDR | 174849 | 2025-10-31
804347 | MS #4 - 20% Acceptance | 240575 | 2025-11-01
805310 | MS #2 - 20% SuperStructure | 58059 | 2025-11-03
805135 | MS #1 - 100% Delivery | 1061807 | 2025-11-04